## Sheet1
Current Customer Testing Environment Issues |  |  |  | 2016-07-15
Issue ID | Issues | Description | Action | ETA*
1350 | Unnecessary ICSC and CCNA required on all Pre-Order Location Inquiries | EASE requires ICSC and CCNA for Pre-Order Location Inquiries, which not required by CORA | This is not functionality issue. In moving to EASE, customers are moving to a larger, more comprehensive ordering system, and common process is important in this larger system. These fields are necessary in order for both customers and CenturyLink know what company/territory they want to do business with for that particular inquiry/order.
1362 | Unable to determine what PON is associated with an emailed response by the subject line | EASE email doesn't list PON on subject line as CORA email | PON information is in the email content Work is in progress | 8//8/2016
1365 | EASE reporting functionality does not appear to be equivalent to the reports provided in CORA | Unable to find a function that will allow to select the information from the ASR and FOC to display a report. Not all fields on CORA reports are on EAES reports | Enhancements will be impalemented after conversion | 1Q2017
1410 | Bill Pack Trailer indicates zero surcharege records | Surcharge is zero | Ready for Testing since June 17
* date may change and CTL will communicate that as soon as known