## 2020 Date Created
ASR GATEWAY/EASE Release 8.0/ASOG 60
Draft Technical Specifications Issued | 2020-01-10
Comment cycle starts | 2020-01-10
Comment cycle ends | 2020-01-28
Final Technical Specifications Issued | 2020-02-07
Testing Available | 2020-02-22
Draft ASR EASE GUI Documentation Issued | 2020-02-24
Comment cycle starts | 2020-02-24
Comment cycle ends | 2020-02-27
Final ASR EASE GUI Documentation Issued | 2020-03-02
Release Production Date | 2020-03-23
ASR GATEWAY/EASE Release 9.0/ASOG 61
Draft Technical Specifications Issued | 2020-07-10
Comment cycle starts | 2020-07-10
Comment cycle ends | 2020-07-28
Final Technical Specifications Issued | 2020-08-07
Testing Available | 2020-08-22
Draft ASR EASE GUI Documentation Issued | 2020-08-24
Comment cycle starts | 2020-08-24
Comment cycle ends | 2020-08-27
Final ASR EASE GUI Documentation Issued | 2020-08-31
Release Production Date | 2020-09-21

## 2019 Date Created
ASR Gateway/EASE Point Release 7.2
Custom Business Rules Notification Issued | 2019-12-20
Comment cycle starts | 2019-12-20
Comment cycle ends | 2019-12-30
Final Custom Business Rules Notification Issued, if required January 3, 2020 | 2020-01-03
Release Production Date | 2020-01-20
SCR120219-1 IMA to EASE Migration
CMP CR Issuance: SCR120219-1 | 2019-12-02
CR Presentation at CMP Meeting | 2019-12-18
Local Service Request Consolidation Plan Due | 2019-01-13
Local Service Request Consolidation Plan Review Meeting | 2020-01-22
Extended Customer Comment Window for Initial Release Notification, Initial Retirement Notice and Consolidation Plan | 2020-02-25
Lumen issues response to CLEC comments including the Final version of the Local Service Request Consolidation Plan | 2020-02-26
Draft Interface Tech Specs | 2020-03-18
Tech Specs Walk-Through | 3/25/20 - 4/15/20
CLEC Comments for Interface Tech Specs | 2020-04-30
Final Interface Tech Specs | 2020-05-15
Product Process Notification associated with Level 2 OSS Changes | 2020-05-15
CLEC Comments due on (New) GUI Release Notes | 2020-06-05
CLEC Comments due on Level 2 OSS Product Process changes | 2020-06-05
Training Aviable | 2020-06-05
GUI Final Release Notice | 2020-06-19
Customer Testing Begins with Local Service Request Consolidation Functionality (120 Days) | 2020-06-05
Customer BETA Test Open | 2020-10-05
Customer Testing Ends | 2021-01-22
Customer Go/No Go Vote | 2021-01-22
Migration to EASE Production | 2021-01-23
Customer Implementation to Production Environment Live on | 2021-01-25
CABS Billing Output Specifications (BOS) Ver 59 March 2020 Release
Draft Technical Specifications Issued | 2019-12-19
Comment cycle starts | 2019-12-19
CenturyLink/CLEC Walkthrough if requested | 2020-01-06
Comment cycle ends | 2020-01-08
Final Technical Specifications Issued January 15, 2020 | 2020-01-15
Testing Available | 2020-01-30
Release Production Date | 2020-03-01

## 2018 Date Created
ASR GATEWAY/EASE New API – NOTE: These dates are to begin testing with impacted customers. | Full implementation in Production is planned for November 2019.
Draft Technical Specifications Issued | 2018-10-19
Comment Cycle Starts | 2018-10-19
Comment Cycle Ends | 2018-10-27
Final Technical Specifications Issued | 2018-11-06
Testing Available | 2018-12-01
Release Production Date | 2018-12-31
CPID/QPID Retirement Application | * Revised Date
Initial CPID/QPID Retirement Notification Issued | 2018-02-23
Comment cycle starts | 2018-02-23
Comment cycle ends | 2018-03-09
Final CPID/QPID Retirement Notificaation Issued | 2018-04-06
Planned CPID/QPID Production Retirement Date | 12/31/19*