## IMA TO EASE CLEC ISSUES LOG
DATE | ISSUE NUMBER | LINKED TO | FROM | EMAIL SUBJECT | ISSUE | PREORDER / ORDER / UOM | TOPIC/FIELD | STATUS | RESOLUTION
2020-06-19 | 1 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE LSR Test Access | Ability to use one ID for all ordering/preordering | ORDER | SIGNON | CLOSED | CUSTOMERS WILL PLACE RSID IN CCNA FIELD
2020-06-29 | 2 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | Additional Testing Credentials Requested : IMA to EASE LSR Test Access | Please set up additional user IDs | --- | TESTING ID | CLOSED | completed
2020-06-29 | 3 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE meeting today | • Confirm if EASE requires the version start with 01 when submitting an order via UOM for both EASE and IMA after the conversion. | ORDER | VERSION | CLOSED | Version can start with any number sequence, but must be incremented for any SUP performed.
2020-06-29 | 4 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE meeting today | • Will check with Lee to confirm that IMA does not do anything for DACT O/I even today. | UOM | DACT | CLOSED | not an EASE issue
2020-06-29 | 5 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE meeting today | • IMA does LQ by WTN and Address, EASE User Guide show we can do LQ by WTN, ECCKT, Address. Chuck will confirm if EASE will support LQ by ECCKT for L-Qwest after the conversion. | PREORDER | WTN | CLOSED | WTN will not be supported. IMA was performing this functionality by having the customer also provide the address. User Guide updated accordingly.
2020-07-08 | 6 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE meeting today | • Confirm in a week if we can submit the in-flight order to EASE. Assuming if it works: o Any order initiated via IMA before conversion that does not require any supplement will complete in IMA. All responses for these orders will return from IMA. – Chuck this is correct. o If an order initiated via IMA, supplement after the conversion to EASE, all responses (FOC, Completion…) after the supplement will return from EASE. – Chuck this is correct. | UOM | INFLIGHT CONV | CLOSED | for UOM customers, inflight pons will be able to be sup'd. This functionality will be available for 90 days after conversion. After that time, UOM orders in IMA, but not sup'd in EASE will have to be re-entered.
2020-07-08 | 7 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE meeting today | • Will check with Lee to confirm that IMA does not do anything for DACT O/I even today. | UOM | DACT | CLOSED | Neustart to check for additional issues.
2020-07-08 | 8 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE meeting today | • IMA does LQ by WTN and Address, EASE User Guide show we can do LQ by WTN, ECCKT, Address. Chuck will confirm if EASE will support LQ by ECCKT for L-Qwest after the conversion. – Loop Qual by ECCKT does not work. | PREORDER | WTN | CLOSED | Information documented in User Guide.
2020-07-08 | 9 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE meeting today | • Confirm if EASE requires the version start with 01 when submitting an order via UOM for both EASE and IMA after the conversion. – I missed this one but just ran a test to check. I was able to submit a UOM through EASE into IMA with VER 00. <LSR_ORD_REQ xmlns="https://imss91-ctp.trendmicro.com:443/wis/clicktime/v1/query?url=http%3a%2f%2fwww.synchronoss.com%2flsr%2fctl%5forder%22%3e&umid=A12836DB-AB6F-5005-B9C5-8448A5C1919D&auth=19120be9529b25014b618505cb01789c5433dae7-dcf7de931d7e8602407f7463e53e0ad09e2a6b8d <HDR> <MESSAGE_ID>XYZTEST3</MESSAGE_ID> <CCNA>R99</CCNA> <TPID>YOURTPID</TPID> <MSG_TIMESTAMP>2020-06-02T10:05:01-06:00</MSG_TIMESTAMP> <PON>XYZTEST33</PON> <VER>00</VER> <LSOG_VER>19</LSOG_VER> </HDR> <LSR> <LSR_ADMIN> <AN>307-777-7777-777</AN> <DTSENT>202006021005</DTSENT> <REQTYP>CB</REQTYP> <ACT>V</ACT> <MI>C</MI> <SUP></SUP> <RTR>C</RTR> <CCNA>A02</CCNA> <CC>A02</CC> <AUTHORIZATION> <NNSP>7606</NNSP> <TOS>1</TOS> <DDD>20200819</DDD> <DFDT>0800</DFDT> <NPDI>D</NPDI> <AUTH_INFO_GRP> <AGAUTH>Y</AGAUTH> <LSP_AUTH_DATE>20200601</LSP_AUTH_DATE> </AUTH_INFO_GRP> </AUTHORIZATION> </LSR_ADMIN> <CONTACT> <INIT>CHUCK ANDERSON</INIT> <INIT_TEL_NO>6233289081</INIT_TEL_NO> </CONTACT> </LSR> <EU> <LOC_ACCESS> <LOCNUM>1</LOCNUM> <NAME>SHAGGY Doo</NAME> <SVC_ADDR_GRP> <SANO>1234</SANO> <SASN>ELM</SASN> <SATH>ST</SATH> <LD1></LD1> <LV1></LV1> <CITY>CHEYENNE</CITY> <STATE>WY</STATE> <ZIP>82001</ZIP> </SVC_ADDR_GRP> </LOC_ACCESS> </EU> <NP> <NP_ADMIN> <NPQTY>1</NPQTY> </NP_ADMIN> <NP_SVC_DET> <PORTED_NBR>3077777777</PORTED_NBR> <NPT>D</NPT> <LNUM>1</LNUM> <LNA>V</LNA> </NP_SVC_DET> </NP> </LSR_ORD_REQ> Thank you Lan | UOM | CONVERSION | CLOSED | there is no limit in EASE to VERSION. Discussed with the customer.
2020-07-22 | 10 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | TEST3PORLD - RAW LOOP DATA QUERY FAILED | Raw Loop Data Query Failed for Assigned | PREORDER | RAW LOOP | CLOSED | referal to IT
2020-07-22 | 11 | 11 | Isaacs, Kim <Kim.Isaacs@allstream.com> | TEST1CTPOAV - Central Add Val - EASE Did Not Require Supplemental | Please see attached – TEST1CTPOAV. IMA requires supplemental address information (UNIT) and returned this as a SAG Only address. EASE Test environment did not ask for supplemental and didn’t flag the address as SAG only. | PREORDER | Address Validation | CLOSED | Modification made to downstream querries. Result should be as expected.
2020-07-22 | 12 |  | Taylor, Nancy <nancy.taylor@Allstream.com> | TEST3PORLD - RAW LOOP DATA QUERY FAILED | RAW LOOP Data querry is taking over an hour to process | PREORDER | PROVIDED TO IT - IMA TEST ENVIRONMENT ISSUE IDENTIFIED | CLOSED | IMA TESTING ENVIRONMENT ISSUE.
2020-07-23 | 13 |  | Matt P <support.mattp@usfamily.net> | I2E | When do I use the REQTYP EB vs MB | ORDER | REQTYP | CLOSED | When doing a 1FR, you would use the REQTYP of EB. When using the U5R, you would use the MB REQTYP. The PS form was only in IMA. EASE will translate the information correctly depending on the REQTYP.
2020-07-23 | 14 | 11 | Isaacs, Kim <Kim.Isaacs@allstream.com> | TEST1CTPOAV - Central Add Val - EASE Did Not Require Supplemental | IMA requires supplemental address information (UNIT) and returned this as a SAG only address. | PREORDER | Address Validation | CLOSED | Modification made to downstream querries. Result should be as expected.
2020-07-23 | 15 | 11 | Isaacs, Kim <Kim.Isaacs@allstream.com> | TEST1CTPOAV AND TEST1PWPOAV - Central and Western Add Val - EASE Did Not Require Supplemental | I’ve attached TEST1PWPOAV – Same issue as TEST1CTPOAV, IMA requires supplemental address (Suite and Building) EASE did not. | PREORDER | Address Validation | CLOSED | Modification made to downstream querries. Result should be as expected.
2020-07-24 | 16 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - follow up with Joe | Can you please let me know how we configure the FROM values for L-Qwest after the conversion? Is the UOM ready for testing in August? Can you provide the connectivity information for RT4 so I can request to set up on our end for Neustar LTE environment testing? Neustar is going to test all REQTYP/ACT and all response types. Will the response generate automatically? Do you need a test plan from us? | UOM | CONVERSION | CLOSED | Joe is addressing with customer.
2020-07-24 | 17 |  | Birchem, Linda <Linda_Birchem@comcast.com> | Comcast/CenturyLink Discussion - IMA to EASE Transition and Testing | 1. Documentation that contains all expected fields for each type of LSR that is supported. Comcast only send Number Portability order Request Type – CB with Act of V. o See attached from the IMA side there is a very detailed document on LSR field by field and also a document on the expected fields that will be returned. url http://www.centurylink.com/disclosures/netdisclosure409.html o The recent turn-up of EASE we found there was gap between the change from 14 to 19 where the field SC ( Service Center) was no longer required. Once in production this was not so and we were told this was defect as SC is required. The value should be defaulted to UOM. In this case this would be a custom rule and an update notification should be sent out. | ORDER | Documentation | CLOSED | This documentation is not availble. Letty W. replied to inquiry 8/13/2020
2020-07-24 | 18 |  | Birchem, Linda <Linda_Birchem@comcast.com> | Comcast/CenturyLink Discussion - IMA to EASE Transition and Testing | 2. Pre-Order functionality expected o CSR – TXTYP = E with TXACT = A We expect that all TNs associated with the account be returned. Today with EASE we do not see this. IMA and all other LECs we get a full disclosure to TNs associated to the account. | PREORDER | CSI | CLOSED | PreOrdering specifics are in the user guide. Letty W. replied on 7/27/2020
2020-07-24 | 19 |  | Birchem, Linda <Linda_Birchem@comcast.com> | Comcast/CenturyLink Discussion - IMA to EASE Transition and Testing | 3. Testing – There should be catalog of testing details like SATE see the url where all the details can be found. o http://www.centurylink.com/wholesale/ima/xml/ | ORDER | TESTING | CLOSED | The test environment is a production look alike. It will not be limited like the IMA SATE environment. CoProviders can re-emulate their produciton orders in test as long as the content has not completed. Letty W. responded on 7/27/2020 and Chuck A. confirmed through email on 8/13/2020
2020-07-27 | 20 |  | isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - PON: TESTLSNEWEAST Unexpected Requirements, Differences, Functionality and Question Regarding Rejects, FOC, DLRs, PSONs, Completion, BCN... | 1. The LSR DCR Field is required in EASE if we request a DLR – In IMA the DRC field is not required, the DLR is emailed to the order initiator. a. Is CenturyLink sending the DRC field to IMA? i. If not, does it need to be required? ii. If yes, is the DRC value going to cause the LSR to drop out of flow through on the IMA side or impact the return of the DLR? | ORDER | DRC | CLOSED | a. Is CenturyLink sending the DRC field to IMA? CTL: IMA does require DRC or FAX NO to be provided when RTR = D and that is an existing IMA edit. i. If not, does it need to be required? ii. If yes, is the DRC value going to cause the LSR to drop out of flow through on the IMA side or impact the return of the DLR? CTL: The DRC sent to IMA will be used in the same manner as it is today in IMA. DRC field does not impact the flow / no flow of an LSR.
2020-07-27 | 21 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - PON: TESTLSNEWEAST Unexpected Requirements, Differences, Functionality and Question Regarding Rejects, FOC, DLRs, PSONs, Completion, BCN... | 2. The LSR APOT field is required in EASE for REQTYP AB – New – In IMA the LSR APOT is not required – this information is derived by the LSR LSO field and the LS CFA field. a. Is CenturyLink send the APOT value to IMA? i. If not, does it need to be required? ii. If yes, is the DRC value going to cause the LSR to drop out of flow through? | ORDER | APOT | CLOSED | For ReqType AB ( Unbundled Loop) there is an edit specific to ACTs N, V, M, or T then either APOT or CFA must be provided. If CFA is provided, then APOT is not forced. If APOT is provided then it is made available through the normal IMA flows. APOT doesn’t alter flow through rules. DRC doesn’t change – it is passed to IMA and flows to the network systems. The DRC delivery methods don’t change and will continue as normal. This is a test env and we don’t pass the orders out to other provisioning systems.
2020-07-27 | 22 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - PON: TESTLSNEWEAST Unexpected Requirements, Differences, Functionality and Question Regarding Rejects, FOC, DLRs, PSONs, Completion, BCN... | 3. EASE LS Form uses the CCEA Field to communicate the termination point, IMA uses the LS Form CFA Field a. Please confirm the mapping CCEA to CFA has been tested and is not causing the orders to drop from flow through. | ORDER | CCEA | CLOSED | 3. EASE LS Form uses the CCEA Field to communicate the termination point, IMA uses the LS Form CFA Field a. Please confirm the mapping CCEA to CFA has been tested and is not causing the orders to drop from flow through. CTL: You will send the data in the CFA field and it will pass to IMA as CFA. You would not send the entry in the CCEA field.
2020-07-27 | 23 | 22 | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - PON: TESTLSNEWEAST Unexpected Requirements, Differences, Functionality and Question Regarding Rejects, FOC, DLRs, PSONs, Completion, BCN... | 4. The doesn’t appear to be the ability to Validate CFA (CCEA) within the EASE LS Form – See screen shot from IMA below. Where is the EASE functionality for validating CFA/CCEA while in Ordering. 4A. This represents a loss of IMA functionality – Please contact the vendor to see if they can accommodate having CFA validation in both Pre-Order and within the LS Screen. Before the go – no-go vote, I would like to know if the vendor can accommodate and if CenturyLink is willing to pay for the enhancement. | PREORDER/ORDER | CCEA/CFA | CLOSED | REFERRAL TO IT - SCREEN SCRAPING ISSUE. 9/8 update: This has been delivered by IT. The demo was conducted on 9/8. 10/6 - CFA Validation confirmed fixed
2020-07-27 | 24 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - PON: TESTLSNEWEAST Unexpected Requirements, Differences, Functionality and Question Regarding Rejects, FOC, DLRs, PSONs, Completion, BCN... | 5. Allstream’s testing will not be complete without confirming that we can receive rejects, FOCs, DLRs, PSON, Completions, BCN – Please confirm that in the test environment, we will receive the responses as requested and that we will get email notices of status changes. | ORDER | RESPONSES | CLOSED | REFERRAL TO IT - NOTIFICATIONS
2020-07-27 | 25 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar pending items - Need help | Chuck to confirm the in-flight order can submit to EASE. (see IMA to EASE – IMPORTANT email subject line) | UOM | UOM INFLIGHT | CLOSED | INFLIGHT PONS CAN BE SUP'D FOR 90 DAYS POST CONVERSION THRU EASE WORK AROUND PROCESS.
2020-07-27 | 26 |  | barker, linda on behalf of Comcast | Comcast/CenturyLink Discussion - IMA to EASE Transition and Testing | 1. Documentation that contains all expected fields for each type of LSR that is supported. Comcast only send Number Portability order Request Type – CB with Act of V. o See attached from the IMA side there is a very detailed document on LSR field by field and also a document on the expected fields that will be returned. url http://www.centurylink.com/disclosures/netdisclosure409.html o The recent turn-up of EASE we found there was gap between the change from 14 to 19 where the field SC ( Service Center) was no longer required. Once in production this was not so and we were told this was defect as SC is required. The value should be defaulted to UOM. In this case this would be a custom rule and an update notification should be sent out. | UOM | UOM | CLOSED | The SC field must be provided on all UOM orders. The IMA difference document only addressed the VFO differences, but we can make a mention of it on there for you. It should already be provided on the UOM requirement information provided from Joe Pavlovich.
2020-07-27 | 27 |  | barker, linda on behalf of Comcast | Comcast/CenturyLink Discussion - IMA to EASE Transition and Testing | 2. Pre-Order functionality expected o CSR – TXTYP = E with TXACT = A We expect that all TNs associated with the account be returned. Today with EASE we do not see this. IMA and all other LECs we get a full disclosure to TNs associated to the account. | PREORDER | CSR BY ECCKT | CLOSED | IT has been able to pull back multiple TNs associated with the account. Cannot re-identify the issues.
2020-07-27 | 28 |  | barker, linda on behalf of Comcast | Comcast/CenturyLink Discussion - IMA to EASE Transition and Testing | 3. Testing – There should be catalog of testing details like SATE see the url where all the details can be found. o http://www.centurylink.com/wholesale/ima/xml/ | 0 | 0 | CLOSED | The referenced documentation as from IMA 14 in 2004. This information is not available from the vendor and will not be provided for EASE.
2020-07-28 | 29 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar pending items - Need help | 2. Chuck to confirm the response type (RT) of L-Qwest after conversion (Need the Response Type post conversion email) | UOM | RT | CLOSED | RT Matrix
2020-07-29 | 30 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar pending items - Need help | 3. Chuck/Letty to confirm if the Account Number field is required when submitting the pre-order Listing Inquiry TXTYP = T for L-Qwest. (RT4 Testing DLI Fail email) | PREORDER | LISTING INQUIRY | CLOSED | AN is not required for ALL listings queries. AN would be used for Account queries.
2020-07-29 | 31 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar pending items - Need help | Provide the updated VFO user Guide to show that EASE support CSR by ECCKT. | PREORDER | CSR BY ECCKT | CLOSED | PROVIDED USER GUIDE
2020-07-30 | 32 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar pending items - Need help | 4. Joe to confirm the Primary/secondary OCN example for one customer so Neustar can update our code (IMA to EASE – follow up with Joe) | UOM | UOM | CLOSED | Addressed with customer.
2020-07-30 | 33 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | TESTLMC2UNE - Failed | Attached is a LCM 2 UNE conversion test – requesting a CHC at 23:00. This is not an unusual order for Allstream as we are consolidating our collocation cages. My PON TESTLMC2UNE, could not be submitted without on APPTCON, the Pre-Order Appointment Scheduler does not list appointments outside of business hours. Will need a solution for this prior to IMA to EASE implementation. Thanks. The attached email is the live IMA order used as a template for this test. | ORDER | 0 | CLOSED | Set times in APPTTIME/DFDT. Set for manual within EASE by using the NRI = Y field.
2020-07-30 | 34 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | Additional Question - : CenturyLink IMA to EASE - UOM API – AllStream | I need to check on something – Our quoting vendor NDA is API connected to IMA and EASE to determine service availability for Wholesale Broadband. My assumption has been that if we are currently operating in with EASE UOM API, there shouldn’t be any testing, certification…that NDA needs to do. Could you confirm my assumption? That after the IMA to EASE migration completes all NDA will need to do is drop the IMA XML API connection. Let me know if this is too simplistic of a view. | UOM | 0 | CLOSED | If it helps, I had a call with Desiree Dortok and Jie Wen (dev) today about this. They do need credentials set up so that they can begin work to develop their IMA LSRs being submitted to EASE. They also are comfortable reaching out to me when their testing is going on, to help resolve speed bumps as they come up. There is going to be a lot of work for them and hopefully early profile setups will get that moving. Chuck Thanks Chuck - We are only using NDA for Pre-Order Loop Qualification for Wholesale Broadband. NDA is currently connected via API to both IMA and EASE. I assume that when the IMA to EASE transition occurs – Desiree will just be able to transfer our IMA queries over to the existing EASE UOM API. I will talk to Desiree about this as well. Thanks.
2020-07-31 | 35 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar pending items - Need help | 5. Joe to confirm when the UOM environment is available for testing? (IMA to EASE – follow up with Joe) • If it is a new connectivity testing, we need the information ASAP so we can request to open firewall and update it on our end. • What is the FROM Value we can set up in LTE for Neustar testing? | UOM | TESTING ENVIRONMENT | CLOSED | Joe responded to Lan about RTE2 hours.
2020-07-31 | 36 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | CSR EASE Testing errors | I received the below report from one of the testers today. TN: 3602544444 OCN: O03 CCNA: ELG Error: oss gateway: the coprovider/contract area combination is invalid | preorder | CSI | CLOSED | Test system has been updated to handle O03 / ELG.
2020-08-01 | 37 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar pending items - Need help | 6. Letty – review and confirm the SCATEG valid values support for TXTYP = O Facility Availability (FA testing RT4 - SCATEG inquiry) Can you confirm that EASE support values “D, H, I, P, or U” in the SCATEG for L-Qwest post-conversion? If yes, could you please update the VFO user Guide to reflect the values? | PREORDER | SCATEG | CLOSED | User guide updated to reflect values
2020-08-02 | 38 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar pending items - Need help | 7. Letty – JB order failed in RT4. (REQTYP JB order fail in RT4) | ORDER | JB REQTYPE | CLOSED | No issues found with JB order submission
2020-08-03 | 39 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar pending items - Need help | 8. Letty – TN Pre-Order Telephone Number Cancellation question (RT4 Testing TN Inquiry/Reserve/Cancel question Email) Today in L-Qwest, after we submit a Pre-order Telephone Number Inquiry and Reserve the TN, we can submit a cancellation for the Reserved TN. I don’t see that option in VFO and could not find any information in the User Guide, either. Can you advise how we can submit a cancel Reserved TN? Can you also share the latest VFO User Guide that support CSR by ECCKT? | PREORDER | TN RESERVATION | CLOSED | The TXACT would be K. That will cause the system to end the transaction.
2020-08-03 | 40 |  | Rebekah Byland <rbyland@popp.com> | Sign up for EASE LSR Testing | POPP has three different LSR IDs, P01, LDB and X60. Currently in the IMA login we are able to select which one we are logging in to from the main screen (the Corporate ID field): In EASE how will we designate which corporate ID we are logging in to? | ORDERING | RSIDs | CLOSED | Right now, you should have testing IDs for each of your LSR IDs. We do have a project in testing that will allow you to log in with one, place the RSID information in the CCNA field and go on with the order. That would allow you to see all the pons in one place, and get navigate between the RSIDs. You should see that functionality in testing in the next couple of weeks as soon as the other code is migrated.
2020-08-03 | 41 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | Directory Listing Order Issues | Allstream is have issues submitting Directory Listing orders - The main issues is CCNA/CC code issues. Allstream has a separate set of CCNA/CC code sets for facilities-based listings. 1. Will Allstream continue to use these CCNA/CC code combinations in EASE? a. If yes, could you add OGT and IOC combinations below so we can submit test orders. b. If not i. What should we use? ii. Will changing the CCNA/CC code combinations for DL requests result in flow through, publishing or billing issues? Thank you. | ORDER | ESP/CCNA/CC | CLOSED | ESP configurations to support multiple RSIDs completed. Job-Aid for RSID use has been provided thru CMP.
2020-08-04 | 42 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - Filtering LSRs | It appears the Filtering in the EASE test environment is filtered to show only my user IDs. I can’t see to remove the filtering (this could be user error) and see other LSRs submitted under O03 credentials. Part of our testing will be having another user pick another user’s LSR and submit a supplement. Could you advise? Thank you. | ORDERING | FILTER | CLOSED | Customer was able to see all pons by checking public.
2020-08-04 | 43 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | ESTCSRECCKT - FAILURE 2020.8.4 | I received different results in EASE and IMA on a CSR by ECCKT query on a loop with a pending disconnect order. Below is the IMA CSR - and attached is the error from EASE. Please consider what will happen if the IMA and EASE account or line status are mismatched. Thank you | PREORDER | CSR BY ECCKT | CLOSED | The SERVIND field needs to be populated with a “N” instead of a “T” when searching by ECCKT. When making this change, we are able to get a valid response in EASE Pre-Order. The user guide has been updated with this change.
2020-08-04 | 44 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Request - Get Rid of Yellow Highlighting | The switch to navigating in EASE vs. IMA will be clunky for users. I think CenturyLink can increase user efficiency by removing the yellow highlighting on fields that are not required when submitting requests to IMA/CenturyLink QC. In my mind yellow highlights should only be used for required fields that a common across the QC, EQ, CT business rules. Otherwise, they quickly become a distraction and quite meaningless. | ORDERING | ORDERING | CLOSED | IT is reviewing this to determine if CenturyLink can make this alteration to the vendor platform. This is recognized as an inconvenience, but is not an intergrity issue for conversion.
2020-08-04 | 45 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | CSR Request Time Outs - Is there a problem with the Test Environment? | Attempting to pull CSR for Colorado TN 7195997769 both yesterday and today, resulting in a Time Out error. CSR pulls without issue in IMA. Thanks. | PREORDER | CSR BY ECCKT | CLOSED | CSR pulls are working in RTE2
2020-08-04 | 46 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | TESTSUPP2ON37 Due Date Change | I attempted to submit a Sup 2 on PON 37 which was in “Sent” status. I received an error indicating that the “LSR/BRC already exists with same CCNA/PON. For LSRs, if supplemental is intended, VER and SUP must be populated. For BRCs, supplementals are not allowed.”. I did use a VER and SUP code – Refresh my memory. Are we only allow to supplement LSRs in EASE when the order has been FOC’d or Rejected? PON 37 will not accept any more supplements because of the status it is in. I get “Supplement is not permitted for this status!” – I suspect this order and supplement will be locked down for the duration of testing. So please look into this issue. So I tried a SUP 3 on PON 35 – I got the same error and now it is stuck in a status issues too. My recollection is we can submit supplements in IMA when the orders is in “Submitted” status – | ORDER | SUP | CLOSED | This is a vendor limitation. Workaround provided is to SUP even though it has not been FOCd.
2020-08-06 | 47 |  | Birchem, Linda <Linda_Birchem@comcast.com> | Request to Delay conversion for no UOM access | Will CenturyLink Delay the IMA conversion | --- | 0 | CLOSED | Confirmed the release is delay to Dec 2020
2020-08-06 | 48 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA to EASE - Neustar FROM TO's for testing | We supposed to have 120 days testing this release. Since we do not have UOM configure and ready to test until next week and there are still many pending questions at this point. Will CenturyLink consider to push out the production date? I don’t think we can wrap up all testing by end of September :-) | --- | 0 | CLOSED | Confirmed the release is delay to Dec 2020
2020-08-10 | 49 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | TEST0810CFAV - CFA Validation on Pending Disconnect Failed | TXNUM TEST0810CFAV is a CFA Validation on a pending disconnect in IMA. There are 2 issues 1.) I purposely did not include the “LAST UNIT” – I expected an error indicating the “LAST UNIT” was required but instead got and “Downstream Error Down/Error – Please try again later”. This type of Error will result in confusion and possibility a call to the CSIE. I’m concerned that the CSIE will be overwhelmed with calls for EASE errors. 2.) When I did populate the “LAST UNIT” – I expected to see a Working CFA in a pending disconnect status. EASE returned CFA not found for requesting party. I populated EASE with the same ACNA as IMA so it appears there are issue with the combined ESP functionality. | PREORDER | CFA | CLOSED | Corrected to match IMA
2020-08-10 | 50 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | TEST0810CFAV - CFA Validation on Pending Disconnect Failed | 3.) When I started playing with the CCNA and ACNA fields I received the following error: Error Code : WG0642 Error Message : couldnt transmit the message to gateway | PREORDER | CFA | CLOSED | Corrected to match IMA
2020-08-13 | 51 |  | Jeanne Kulesa <jeanne.kulesa@synchronoss.com> | PON JLKL3IMAEASE1 Reject for IMA<==> EASE | In PROD for CTL Embarq UOM LSOG19, we sent PON 235213376 with TOS, and it got a FOC. But in Test for the IMA cutover, this PON JLKL3IMAEASE1, we received a reject. CODE:CTLS1001¦DESC:Invalid REQTYP / TOS combination (system) | ORDER | TOS | CLOSED | IMA to EASE: TOS needs to be IMA format (single digit 1 and no dashes) AN needs to have dashes DFDT is going to be needed for the order. You could do 0800-1900. PORTED_NBR if it is a single number doesn’t need the -9949, if it is a range then the Low and High should be different.
2020-08-14 | 52 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | IMA - EASE REQTYP MB support in RTE2 VFO Question | Hi Letty/Chuck, We have customers submit the following product/Reqtyp to Qwest IMA today. In the IMA EASE difference doc, I could see EEL (product 26) REQTYP M in IMA converts to K in EASE. I did not see any changes mention for product 25 & 29. I assume that we will use the same REQTYP M when submitting in EASE after the conversion, but when I create an order in VFO for product 25 using REQTYP M, I don’t see the PS form.. Can you please confirm which REQTYP and Forms EASE will support for product 25 and 29? PRODUCT NAME IMA REQTYP IMA PROD IMA LSR FORMS SUPPORT EASE REQTYP EASE LSR FORMS SUPPORT # UNE-P ISDN BRI M 29 LSR, EU, RS, DL ? ? UNE POTS (P or STAR) M 25 LSR, EU, PS, DL ? ? EEL/UNE Combination M 26 LSR, EU, RPL, DL K LSR, EU RPL DL | ORDERING | REQTYPE | CLOSED | See IMA to EASE differences document for detailed explaination of values.
2020-08-10 | 53 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | RTE2 testing failed for Pre-order LIsting Telephone Inquiry (DLI) | Hi Chuck and Letty, I tried to submit a DLI using the same LTN we have in production but received an error. PROD: TXNUM = NDLI18269149 RTE2: TXNUM = RT2NDLI18269149 | PREORDER | LISTING INQUIRY | CLOSED | EASE LSR guide updated with different values.
2020-08-14 | 54 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | RTE2 testing failed for Pre-order LIsting Telephone Inquiry (DLI) | Hi Chuck and Letty, I reported the DLI issue since July in VFO RTE4, and then again in RTE2. I am not sure if it is a configuration issue or if it is system issue on your end. Could you please help me to check? I tried with different TN from production and they all failed  | PREORDER | LISTING INQUIRY | CLOSED | DLI mapping issue resolved.
8/18/.20 | 55 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | RTE2 testing failed for Pre-order LIsting Telephone Inquiry (DLI) | RTE2 testing failed for Pre-order LIsting Telephone Inquiry (DLI) | PREORDER | LISTING INQUIRY | CLOSED | DLI mapping issue resolved.
2020-08-21 | 56 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> | EASE LSR User Guide - Feature Availability question | Hi Letty, I just noticed that the required fields listed under the Feature Service Availability (page 66-67) in the EASE document are not correct. It looked like they copied from the Telephone Number Inquiry section. I believe Qwest only require NPA-NXX, TOS and STATE fields in IMA for Feature availability. I am not sure if there is any additional fields required after this conversion. | PREORDER | FEATURE SERVICE AVAILABILITY | CLOSED | EASE LSR User Guide has been updated.
2020-08-25 | 57 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - Need to Change Font or avoid using Capital I : VFO Email Confirmation Verification Code | I received the below verification code I typed in “zlqen” got an invalid code error. When I copied and pasted into VFO – I saw that what I thought was lower case “l” was really and upper case “I”. Just trying to save the CenturyLink IT Helpdesk some calls | SYSTEM | VERIFICATION CODE | CLOSED | Controlled by the Vendor. Referred to the vendor for future possible enhancements.
2020-08-26 | 58 |  | Nguyen, Lan <Lan.Nguyen@team.neustar> Barker, Linda E <Linda.Barker@CenturyLink.com> Isaacs, Kim <Kim.Isaacs@allstream.com> | RT VALUE MATRIX | Matrix will show what IMA was using and what to expect go foward in EASE. | ORDERING | RT VALUE MATRIX | CLOSED | Created RT matrix for IMA to EASE conversion
2020-09-08 | 59 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE TESTING - Errors and Test Orders Processed Through Billing Completion | We are experiencing issues submitting the below PONs in the test environment. The “Errored” PONs are getting an “Internal Processing Error”. The PON MN13TEST – received a reject but the reject does not provide the reject reason. Just a reminder – The PONs in “Sent” status have been in that status for quite some time. Just a reminder, it is Allstream’s expectation all of the PONs we successfully submit in the Test environment will be processed through each status (i.e. reject/FOC, DLR (if applicable), PSON, jeopardy, to billing completion). MNTESTD3 Errored MNTEST3 Errored MNTESTD2 Sent MN13TEST Rejected (non-Fatal) MN12TEST Sent | ORDERING | Order Issue | CLOSED | Issues regarding the specific pons have been addressed thru various fields. EASE edit to require CCNA populatation with RSID value has been created.
2020-09-08 | 60 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE TESTING - Errors and Test Orders Processed Through Billing Completion | Speaking of PSONs and DLR - 1. Where will we find the PSONs in EASE LSR or will they just be email? 2. Please confirm that the DLRs for applicable UNE Loops will be in CEMR 3. xDSL Loop testing – Will there be any change to how the test results (PTA) are provided? | NOTIFICATION | Notification Issue | CLOSED | PSON and Comp notices were issued this week with data in the sections. Some review still remains.
2020-09-08 | 61 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE TESTING : NEW IDs merger of ESP IDs into single sign on Job Aid Not Matching EASE Order Initiation | Allstream’s new set of credentials do not appear to be set up as a Managed ESP (multiple RSID) User - Below is the Order Initiation screen Allstream receives – It doesn’t have the Managed ESP options. We can’t test submitting orders using all our RSID, CCNA, CC codes. Thank you | ORDERING | Single Sign on | CLOSED | RSID final process has been distributed
2020-09-08 | 62 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE TESTING TESTLNPCC Still getting "Internal Processing Errors" | Trying to submit PON TESTLNPCC, receiving Internal Processing Errors - | ORDERING | Order Issue | CLOSED | Issue resolved
2020-09-08 | 63 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE TESTING - IMA vs EASE Difference - Telephone Number Formatting "-" Wish List | When entering an Account Number (AN) in IMA, IMA automatically inserts the hyphen. In IMA users enter NPANXXNNNN and IMA reflects NPA-NXX-NNNN. For REQTYP CB – EASE will allow user to enter NPANXXNNNN but will error the LSR stating a AN needs to be 12 or 16 characters. Allstream is finding the EASE requirements for manually adding hyphens to a TN format are inconsistent. For example, WTNs for CSI, Loop Quals do not require hyphen, AN on CB request requires hyphens, Ported Numbers do not require hyphens. If EASE cannot automatically add the hyphen for TN formatted fields, can you at least make the requirements consistent. | ORDERING | Formatting Issue for AN field | CLOSED | EASE will remove all formatting and reformat this field as needed by IMA systematically.
2020-09-08 | 64 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - Reject on MN13TEST V1.0 “This PON/VER combination has already been used | The Reject response for PON MN13TEST V1.0 is now populated with the reject reason. But we are having trouble understanding the reject – It says “This PON/VER combination has already been used” – The user doesn’t recall submitting MN13TEST V1.0 twice, can you explain what caused EASE/IMA to think we had used the PON before? Thanks | ORDERING | Duplicate PON | CLOSED | The PON / VER which was entered by another user. PON information provided back to the customer for verification
2020-08-04 | 65 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | TESTCSRECCKT - FAILURE 2020.8.4 | Hello - I received different results in EASE and IMA on a CSR by ECCKT query on a loop with a pending disconnect order. Below is the IMA CSR - and attached is the error from EASE. Please consider what will happen if the IMA and EASE account or line status are mismatched. Thank you | PREORDER | CSR by ECCKT | CLOSED | Issue has not been replicated in migrated test enviornments
2020-08-28 | 66 |  | Lan.Nguyen@team.neustar | IMA - EASE - Request BCN XML example | Qwest support BCN (Billing Completion), I did not see it in the 2Q19 schema. Could you please provide an example of how EASE will send the BCN post-conversion for L-Qwest in UOM? (I emailed this question to Chuck and Letty on 08/07, and want to add to the cmp to include in the log) | NOTIFICATION | Billing completion | CLOSED | Sent XSD to LAN on 9/21
2020-09-15 | 67 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - PSON Discrepancies | I’m finding that PSONs in EASE are not completed - Attached are a PSON from EASE and an email of a PSON from IMA. Please explain why the EASE PSONs are incomplete? Is the incomplete PSON due to the test environment? If so, how can we arrange to see a complete PSON in EASE. Thank you | NOTIFICATION | PSON | CLOSED | PSON is generated from the SOP service order and yes there will be a wide variety depending on how the order was constructed. Full Auto will hit closer, manually fixed pretty close, manually done with no SOP work would not be close. If they are questioning structure difference is one thing, content is different and can vary with this effort. PSON and Comp notices were issued this week with data in the sections. Some review still remains.
2020-09-16 | 68 |  | Lan.Nguyen@team.neustar | IMA to EASE - Loop Order Testing reject for LINESHAREDTN | Submitted Loop Order (REQTYP AB), PON LT9007369 populated SLTN with 5052993840 and receive rejected: <ERROR_MESSAGE>LS Form:Service Details Section 1:LINESHAREDTN invalid format</ERROR_MESSAGE> LINESHAREDTH is replaced by SLTN. 1. Why do we receive this reject? 2. Can you confirm that SLTN should not contains any hyphen? I believe all Telephone format send to EASE should not have hyphen. | ORDERING | Reject error (REQTYP AB) PON LT9007369 populated SLTN with 5052993840 | CLOSED | Error messages have been updated to reflect the requested changes.
2020-09-17 | 69 |  | Sarita.Singhal@team.neustar | Testing Reject for CSR FEAT_PP_DESCIND field | Submitted CSR Preorder Request , TXNUM CSRQW91602and received below error : <PRESPD>USOCDESCIND must be Y.</ PRESPD> While this field name changed to FEAT_PP_DESCIND. 1. Why do we receive this reject? | PREORDER | Reject error (CSR) TXNUM CSRQW91602 | CLOSED | Error messages have been updated to reflect the requested changes.
2020-09-17 | 70 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing reject for FBDLCCNA | Submitted Number port Order (REQTYP CB), PON TESTQWNP91604 and received below error : <ERROR_CODE>DL FBDLCCNA900</ERROR_CODE> <ERROR_MESSAGE> DL Form 1:Listing Control Section:FBDLCCNA is required on first DL form</ERROR_MESSAGE> And <ERROR_CODE>DL FBDLCC 900</ERROR_CODE> <ERROR_MESSAGEDL Form 1:Listing Control Section:FBDLCC is required on first DL form</ERROR_MESSAGE> But FBDL CCNA and FBDL CC is replaced by LSR Form CCNA and LSR Form CC field. 1. Why do we receive this reject? | ORDERING | Reject error (REQTYP CB) PON TESTQWNP91604 | CLOSED | Error messages have been updated to reflect the requested changes.
2020-09-17 | 71 |  | ISAacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - Error - Internal Processing Error | Could you tell me what the error is on PON TESTRSIDNEWCFA? I’m getting an Internal Processing Error on this one. Thank you. | ORDERING | Internal Processing Error (PON TESTRSIDNEWCFA) | CLOSED | ‘CCNA was required on the pon’
2020-09-16 | 72 |  | Lan.Nguyen@team.neustar | IMA- EASE Question for HTSEQ | Hi Chuck, Could you please advise how do we submit the HTSEQ to EASE. Sorry, I did not understand the example provided in the IMA to EASE Difference doc. I attached an example of PON in production and copy the HTSEQ section below , can you let me know how should I enter the HTSEQ post conversion? <HGI> <LOCNUM>1</LOCNUM> <HNUM>001</HNUM> <HA>N</HA> <HNTYP>2</HNTYP> <HTSEQ>435-529-7434,435-529-7435,435-529-7433,435-529-7436</HTSEQ> <HUNT_DET_INFO> <HLA>N</HLA> <NOTYP>T</NOTYP> <HTN>435-529-7434</HTN> </HUNT_DET_INFO> <HUNT_DET_INFO> <HLA>N</HLA> <NOTYP>T</NOTYP> <HTN>435-529-7435</HTN> </HUNT_DET_INFO> <HUNT_DET_INFO> <HLA>N</HLA> <NOTYP>T</NOTYP> <HTN>435-529-7433</HTN> </HUNT_DET_INFO> <HUNT_DET_INFO> <HLA>N</HLA> <NOTYP>T</NOTYP> <HTN>435-529-7436</HTN> </HUNT_DET_INFO> </HGI> | ORDERING | HTSEQ to EASE submission | CLOSED | HTN was submitted without dashes and we handle formatting on handoff to IMA with dashes.
2020-09-17 | 73 |  | Lan.Nguyen@team.neustar | IMA- EASE Question for HTSEQ | I have a few more questions: Does it mean all HTN Belong to the HNUM 001 will all have “A” in the HTSEQ? If customer has another HNUM 002, all HTSEQ associate with this HNUM will populate with “B”? If a customer populates all “A” in the HTSEQ, how do you know which HTN is first, next, and last? Do you go by the sequence of the HTN send in the order? Can customer using 1, 2, 3 in the HTSEQ or only alpha? | ORDERING | HTSEQ to EASE submission | CLOSED | I just picked A to group them. If there was another Hunt Group then you would group them with something not A – I believe B is correct. We “build” the Hunt Sequence in order submitted. 1st entry is the first in the sequence, 2nd entry is the next, and so on. It’s the same format rules For Series Hunt Groups, the format is 1 to 4 alphanumeric characters, i.e.: • A or AN • AA or AAN • AAA or AAAN For Muli-Line Hunt Groups the format is 4 or 5 numeric characters • 0123 • 01231
2020-09-17 | 74 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing reject for DLECCCNA | Submitted Loop Order (REQTYP AB), PON TESTQWESTAB91701 and received below error : <ERROR_CODE>LSRDLECCCNA003 </ERROR_CODE> <ERROR_MESSAGE LSR Form:Admin Section:DLECCCNA required </ERROR_MESSAGE> But DLECCCNA is replaced by LSR Form CCNA Why do we receive this reject? | ORDERING | Rejection issue (DLECCCNA) | CLOSED | Error messages have been updated to reflect the requested changes.
2020-09-17 | 75 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - Expected Circuit Ownership Edit Was Not Presented | Hello – I submitted PON TESTRSIDERROR (REQTYP AB ACT D) with the intent of triggering an RSID/CCNA/ACNA error. Circuit ID 3.LXFU.586376..NW carries and RSID/ZCID of O03 ACNA OGT. I was able to submit this PON using A07/AYD without receiving an error. Will I get a reject at some point? | ORDERING | Owenership Validation | CLOSED | Adapted the edit to ensure an upfront validation and rejection when not correct.
2020-09-17 | 76 |  | isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - LOCNUM Should Be Added to the Differences List | Hi – IMA GUI auto-populates the “LOCNUM” field – EASE requires the user to enter the LOCNUM. Could add this to the differences list. Thanks. | ORDERING | EASE recommendation | CLOSED | Addressed in the current IMA to EASE differences document.
2020-09-18 | 77 |  | Lan.Nguyen@team.neustar | pon LT3811173R3585 | the TOS of 1B not being supported on an ACT of C | ORDERING | TOS issue | CLOSED | TOS edit is occurring on value of 1. Looking at IMA code for 1B.
2020-09-21 | 78 |  | Lan.Nguyen@team.neustar | REQTYP MB - Received Incorrect error message | Submit LT3811086R3585A REQTYP MB, ACT = V, populated RS Form and received incorrect error message: PS Form:Service Details Section 1:TNS cannot be BTN when ACT is Z and LNA is N or D When convert IMA to EASE, ACT Z change to ACT V and ELT = A. PS form is replaced by RS form Qwest should reject for ACT V and the RS form after the conversion. | ORDERING | Order Issue | CLOSED | IMA development is correcting the error message
2020-09-21 | 79 |  | Lan.Nguyen@team.neustar | IMA - EASE Conversion - CHC values mapping | IMA support CHC values: Products 3, 4, 7, 9, 9a, 10, 11, 12, 15, 16, 17, 18, 19, 20, 21, 30, 31, 34, 35, 39, 40, 41, 42: Y = Yes N = No Products 4, 7, 24, 41, 42: B = Batch Hot Cut (CenturyLink specific) EASE Support CHC values: Please provide the CHC values for EASE A = Large job B=Batch Y=Yes Please provide the map from IMA to EASE for the CHC field and update the IMA to EASE Different doc. | ORDERING | IMA - EASE Conversion | CLOSED | Addressed in the current IMA to EASE differences document.
2020-09-17 | 80 |  | isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Testing - Expected Circuit Ownership Edit Was Not Presented | I submitted PON TESTRSIDERROR (REQTYP AB ACT D) with the intent of triggering an RSID/CCNA/ACNA error. Circuit ID 3.LXFU.586376..NW carries and RSID/ZCID of O03 ACNA OGT. I was able to submit this PON using A07/AYD without receiving an error. Will I get a reject at some point? | ORDERING | Circuit Ownership Validation | CLOSED | For PON, CSR was not able to be pulled and dropped to manual task. In production, analyst would have validated ownership against CSR and rejected PON. Will continue to work on editing for orders to ensure that ownership validation is an UPFRONT edit in EASE
2020-09-22 | 81 |  | Lan.Nguyen@team.neustar | IMA to EAST TESTING pending for Response | Hi Chuck I submitted the following PON via UOM and have not received responses. Could you please review and send FOC, BCN and Completion? PON REQTYP ACT Product Lan Note LTN00043288311 CB V Number Port FOC, COMP issued. BCN tbd FOC is good– COMP does not return the same information that we receive from IMA today Please confirm if the difference is missing details form the sections like Bill and S&E. If that is the case, its probably my issue and I can bring in an order typist on other orders to correctly build it. LTN00043247760 CB V Number Port FOC, COMP issued. BCN tbd FOC is good– COMP does not return the same information that we receive from IMA today. Same as above LTN00043182519 CB V Number Port FOC, COMP issued. BCN tbd Did not receive the response I am researching this but the HDR missing the VER tag appears to be a problem. We are looking at adding an edit for that element to prevent the confusion. LTN00043157316 JB C Directory Listings/Assistance AC (FOC), and AT (Comp) sent. No BCN. Did not receive the response Same as above – missing VER LT3811086R3585A MB V UNE-POTS Missing CC field prevents submission to IMA. Did not receive the reject for CC? For REQTYP MB, CC is not a required field today for IMA. Are you saying that CC is required for all REQTYP when submitting to EASE via UOM? Also, did you send a reject for the CC as I did not receive them? I am double checking with the team on this item. LT3811173R3585 MB C UNE-POTS Errored – invalid reqtype / TOS (the TOS 1B issue). Please resend with CC field populated and it should work. Same as above Same as above LT9007371 AB D Loops Missing CC field prevents submission to IMA. Did not receive the reject For REQTYP AB, CC is not a required field today for IMA. Are you saying that CC is required for all REQTYP when submitting to EASE via UOM? Same as above | ORDERING | Responses | CLOSED
2020-09-28 | 82 |  | Lan.Nguyen@team.neustar | IMA - EASE Feature Activities (FA) value conversion question | In IMA FA - Feature Activities Valid Values: Products 11, 12, 18, 20, 25: N = Add C = Change (old values) D = Disconnect V = Conversion as specified T = Change (new values) EASE valid values: <xs:enumeration value="C"/> <xs:enumeration value="D"/> <xs:enumeration value="I"/> <xs:enumeration value="N"/> <xs:enumeration value="O"/> <xs:enumeration value="V"/> <xs:enumeration value="W"/> What values should we map for “T” from IMA to EASE. Please update the IMA to EASE Difference document. | ORDERING | value conversion | CLOSED
2020-09-25 | 83 |  | isaacs, Kim <Kim.Isaacs@allstream.com> | Need All PONs Processed Through Billing Completion Notice | Hello – Allstream needs to see all the test orders it has submitted move through all status and for CenturyLink to email all responses to order initiators. This includes - FOC or Reject, if applicable, PSON, CN, BCN. Despite multiple requests to move orders through each status and email responses, CenturyLink has not completed this task. I’m have trouble convincing my testers to spend their precious time submitting test requests when there has been no response to the first batch of test LSRs. Please recall, the Allstream has automation built to transcribe the IMA email responses. We will need to know the difference between the IMA and EASE email responses to be prepared for the December migration. This is a very important piece of our test plan and to date we have not seen any emailed responses on our test orders. Thank you | ORDERING | Billing Completion Notice | CLOSED | monitoring status to adjust/FOC daily.
2020-09-25 | 84 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA TO EASE Address Validation Discrepancies | Hello – I am having difficulties getting an address to validated in the same format as IMA. EASE TXNUM ADDVAL924UT will not validate the address with LD2: FLR LV2: 1 as IMA does see below. I am concerned that if an EASE LSR is submitted with LD1: FLR and LV1: 1 (as it validates in EASE), the LSR will drop out for manual handling. Why do IMA and EASE validate addresses differently and how will that impact flow through. Select Address Validation Type: X__Validate by Street Address ___Validate by Telephone Number | ORDERING | IMA TO EASE Address Validation Discrepancies | CLOSED | All order forms with address information will handle mappling to correct LD LV elements.
2020-09-29 | 85 |  | ISaacs, Kim <Kim.Isaacs@allstream.com> | IMA TO EASE TEST TXNUM ADVAL929EQ | I was attempting to see what happens when I validate an EQ address using an RSID in the CC Field of the Query Test Address 2475 S Arden St, Las Vegas, NV 89104 TXNUM ADVAL929EQ Interesting – I get a near match. Frustrating – The near match options provided by EASE has the supplemental address information in the AAI field. Regardless of where I put the supplement address information I cannot get an exact match. I have faced the same frustration when using EASE to validate near matches QC territory so my issue is IMA allows the user to select the supplementation address options and EASE requires the user to “Change” the query. I thought EASE was going to be updated so the users could choose supplemental address information from the near match options. When can we expect to see this functionality? Thanks | PREORDER | Testing | CLOSED
2020-09-30 | 86 |  | Lan.Nguyen@team.neustar | Pre-Order Listing Telephone no response | Hi Letty, Is there any issue with the Listing Telephone Inquiry in VFO (TXTYP T)? I submitted a couple LTN from production to RTE4, TXACT (lower section) = T and did not receive any response LTN: 5072584540 3073371601 | PREORDER | Responses | CLOSED | IT has discovered a minor coding/mapping problem that will be fixed by 10/2 afternoon.
2020-10-02 | 87 |  | Lan.Nguyen@team.neustar | IMA TO EASE TESTING - REQTYP MB convert to KB failed | Copy an existing production EEL Order LT7919576-1BAUDSC REQTYP MB ACT = D in IMA, convert to KB ACT D submit to EASE RTE4 PON LT7914938-BAUDSC receive reject “RPL Form:Admin Section:Number of address location sections must equal the number entered in RSQTY”. Today IMA does not require the address location sections. Please advise why we receive this reject and how to submit KB order. | PREORDER | Testing | CLOSED | CenturyLink IT altered mapping to resolve this issue.
2020-10-02 | 88 |  | Lan.Nguyen@team.neustar | IMA to EASE TESTING - EEL MB ACT C convert to KB ACT C failed | Receive different result in EASE versus IMA for EEL order. Clone production EEL order (PON LT3805960R2253) REQTYP MB, ACT C, convert to KB ACT C (PON LT LT3805960R2253) submitted in RT4 and receive reject RPL Form:Admin Section:Number of Secondary Location Service Details must equal the number of Secondary Location Sections RPL Form:RPL Secondary Location Section 1:CALA required when ZIP not provided and RSQTY is 2 and LIT is E | PREORDER | Testing | CLOSED | CenturyLink DEV team fixed all of the RPL issues in EASE mapping to IMA. IMA Currently only takes LSR and RPL forms. EASE mapping currently takes NAME and NCON from the EU form and maps it to the RPL PRILOC / SECLOC and wipes out the EU form We have adjusted our logic to take location information from the End user form. AFT, SAPR, SANO, SASF, SASD, SASN, SATH, SASS, LD1, LV1, LD2, LV2, LD3, LV3, AAI, CITY, STATE, ZIP And place them into the PRILOC / SECLOC matching elements on the RPL form. And IF for some reason both EU and RPL locations are filled out, then only the NAME / NCON values from EU will be used and we will keep the provided RPL PRILOC/SECLOC data.
2020-10-05 | 89 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | Need additional CCNAs, OCNs added for Directory Listing Testing | Hello – Could you add the below CCNA and OCNs to EASE testing environment so we can test FBDL requests? Thank you CCNA CC AYD 9103 OGT 5744 OEY 5538 ELG 0802 ATG 0432 PCL 0955 | PREORDER | Testing | CLOSED | Your request has been completed.
2020-10-05 | 90 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - CenturyLink Online Listings Viewer. | Can you confirm there will be no changes to DLIS and CenturyLink Online Listings Viewer after the migration in December. Thank you | PREORDER | IMA to EASE onlie listing viewer | CLOSED
2020-10-07 | 91 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing reject for RPL NAME Field | Submitted Resale Private Line (REQTYP KB), PON TESTQWKB10701 and received below error : <ERROR_CODE>RPLNAME 900</ERROR_CODE> <ERROR_MESSAGE> RPL Form:RPL Primary Location Section:NAME required when ACT is N, D, W, V or C </ERROR_MESSAGE> But as per IMA to EASE doc, RPL Primary Name and Secondary Name is no longer supported. (“Derive from NAME field on End User form”). | PREORDER | Testing reject | CLOSED | CenturyLink DEV team fixed all of the RPL issues in EASE mapping to IMA. IMA Currently only takes LSR and RPL forms. EASE mapping currently takes NAME and NCON from the EU form and maps it to the RPL PRILOC / SECLOC and wipes out the EU form We have adjusted our logic to take location information from the End user form. AFT, SAPR, SANO, SASF, SASD, SASN, SATH, SASS, LD1, LV1, LD2, LV2, LD3, LV3, AAI, CITY, STATE, ZIP And place them into the PRILOC / SECLOC matching elements on the RPL form. And IF for some reason both EU and RPL locations are filled out, then only the NAME / NCON values from EU will be used and we will keep the provided RPL PRILOC/SECLOC data.
2020-10-07 | 92 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing reject for LSR RSTTYP Field | Submitted Resale (REQTYP EB) order, PON TESTQWESTRS92801 and received below error : <ERROR_CODE>LSRRSTTYP 003</ERROR_CODE> <ERROR_MESSAGE>LSR Form:Admin Section:RSTTYP required when ACT is B </ERROR_MESSAGE> But as per IMA to EASE doc, LSR RSTTYP is no longer supported. (“Discontinue use of RSTTYP field as RS form LNA field data will be used”). | PREORDER | Testing reject | CLOSED | CenturyLink DEV team fixed all of the RPL issues in EASE mapping to IMA.
2020-10-08 | 93 |  | Lan.Nguyen@team.neustar | IMA-EASE TESTING - Missing RESP/RESPC in the Listing Telephone Preorder response | Submitted Preorder Listing Telephone Inquiry via UOM TXTYP = LT3074739463T, LT5418551528T TXTYP = T, TXACT (body) = T Receive Response from CenturyLink without RESPC/RESPD section below <RESP_STATUS_GRP> <RESPC>27</RESPC> <RESPD>Transaction Successful</RESPD> <PRESPC>27</PRESPC> <PRESPD>Owner: CLEC: </PRESPD> These fields are required in the response, please review the issue ASAP as it is blocking our testing for Listing Telephone Inquiry. I attached one XML Response example we received today. | PREORDER | Testing reject | CLOSED | RESPC/RESPD and PRESPC/PRESPD has been added to the responses.
2020-10-08 | 94 |  | Lan.Nguyen@team.neustar | IMA-EASE TEST Listing Telephone Inquiry TXACT = S failed | Submitted Listing Telephone Inquiry TXNUM = LT5418551528S, TXTYP = T, TXACT (Body) = S via UOM Receive response with RESPC = 27 successful but no listing information return in the response See attached XML request and response | PREORDER | Testing reject | CLOSED | Customer is receiving expected response for DLI.
2020-10-09 | 95 |  | isaacs, Kim <Kim.Isaacs@allstream.com> | 10/9/2020 - IMA to EASE CLEC call | Need to determine how line loss notifications are provided to customer and how they are visable. | NOTIFICATIONS | Line Loss Notifications | CLOSED | Line Loss notifications are now provided via email.
2020-10-12 | 96 |  | Lan.Nguyen@team.neustar | IMA-EASE AV alternative Address with incorrect RESPC | Submitted an Address Validation: 849 FRONT ST EVANSTON WY, 82930 Received 2 addresses in the response but the RESPC/RESPD return via UOM has 42/Exact Address Match Found. See attached TXNUM LTQWS00002798916 Since there are 2 address returned, CL should return the RESPC= 5, RESPD = Address Near Match Found/Alternatives Provided. | PREORDER | Address Validation | CLOSED | CenturyLink is returning RESPC=5, with Exact Address Match with Sub-addresses Found Qwest Territory
2020-10-12 | 97 |  | Lan.Nguyen@team.neustar | IMA - EASE TEST Number Port with multi-line Listing failed | Submitted LSR order REQTYP CB with 2 Directory Listing and received invalid reject for OCCNA and OCC PON = LTCHAR180959 Received reject : DL Form 2 Listing Control Section:LSR Form:Admin Section:OCCNA is prohibited DL Form 2:Listing Control Section:LSR Form:Admin Section:OCC is prohibited | ORDER | Invalid Reject | CLOSED | CenturyLink IT altered mapping to resolve this issue.
2020-10-13 | 98 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing reject for RS PRIDB and PTKCON Field | 1. Submitted Resale (REQTYP EB) order, PON QWEB101301 and received below error : ERRORCODE: RS PRIBD 900 ERRORMESSAGE: RESALE Form:Service Details Section 1:PRIBD required for PRISDN_TRK But as per IMA to EASE doc, RS PRIDB is no longer supported. (Data is provided on the IS form) 2. Submitted Resale (REQTYP EB) order, PON QWEB101301 and received below error : ERRORCODE: RS PTKCON 900 ERRORMESSAGE: RESALE Form:Service Details Section 1:PTKCON required when LNA is N, V or T But as per IMA to EASE doc, RS PTKCON is no longer supported. (Data is provided in TTP field on DDPS form) | ORDER | Testing reject | CLOSED | CenturyLink has updated the error message to correct the form and show the IBPS message
2020-10-13 | 99 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing reject for EU AHN Field | Submitted PON TESTQWAB100803 and received below error : ERRORCODE: EU AHN 001 ERRORMESSAGE : : EU Form:Location Access Section 1:AHN required for unnumbered address But as per IMA to EASE doc, EU AHN is no longer supported. (When AHN is necessary populate AFT with C (Provider assigned house number) and provide AHN numeric data in SANO field) | ORDER | Testing reject | CLOSED | AHN error modification completed.
2020-10-13 | 100 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing reject for DL DACT Field | Submitted JB order PON QWJB101207 for DACT value as I and received no reject for DACT valid value. But as per out understanding since now only one occurrence on Delivery Address Section is supported, DACT only valid value supported are N and D, not I or O. Can you please confirm. | ORDER | Testing reject | CLOSED | CenturyLink confirmed this is a correct statement - one occurrence on Delivery Address Section is supported, DACT only valid value supported are N and D, not I or O.
2020-10-16 | 101 |  | Frid, Kate <kjfrid@Allstream.com> | IMA to EASE Testing ¦ Pre-Order Issue on LSR PON KF5202829T1 | This is the issue I brought up on the call today, when writing LSR’s there is a “Search Pre-Order” link on certain sections of the LSR, which allow you to select items that were validated in pre-order, such as addresses and CFA’s. PON: KF5202829T1 I used the search pre-order function to populate the CFA field (which put a “/” where there needs to be a space) and it seemed like no matter what I changed, I was not able to get rid of the error which states: | ORDER | CFA PREORDER NOT LINKING IN ORDER | CLOSED | ACNA on the LSR page should match the ACNA used to order the CFA. In this instance the order was updated to AYD and the errors were cleared.
2020-10-16 | 102 |  | Frid, Kate <kjfrid@Allstream.com> | IMA to EASE Testing ¦ Pre-Order Issue on LSR PON KF5202829T1 | There actually is one other issue I forgot to mention on the call, which is, is there a reason why we cannot use dashes in our PONs in EASE? This is a function that we are able to use in IMA today. CLINK EASE ASR does allow dashes in PONs as does the legacy Level 3 instance of VFO, therefore I don’t understand why this is limited in EASE LSR VFO. Allowing dashes in PONs makes searching by partial PON info in email and other systems much quicker and easier. Dashes in PONs also helps more easily identify key markers on PONs, such as the product and people who submit the LSRs. I would consider this a short-coming of EASE LSR as compared to IMA if we are not able to use dashes in our PONs. Has this already been addressed? | ORDER | USE OF SPECIAL CHARACTERS IN PON | CLOSED | Allowing a hyphen/dash in the PON has been implemented.
2020-10-19 | 103 |  | Lan.Nguyen@team.neustar | TN format submit in IMA - Urgent | We just noticed today that in the IMA to EASE you change the format of all TNS to allow hyphen, is that correct? We already complete the major of our code for this release to remove the hyphen when submitting orders to EASE for Qwest. We cannot reverse the code at this time. | ORDER | TN format submit in IMA | CLOSED | CenturyLink modified the BRMS rule and made accommodations to accept the TN format with or without dashes
2020-10-20 | 104 |  | Lan.Nguyen@team.neustar | Resale Private Line Form DQTY question | In the IMA RPL form today, Qwest rules DQTY must 2-10 (allow 1 alpha character) IMA to EASE Document mention that rule only allow 3 characters Does it mean we must submit as 001, 002,003….in the DQTY? Why can’t EASE accept 1 character like IMA does today? | ORDER | DQTY Question | CLOSED | Leading zeros are not requried. For example: 1, 2 or 3 are acceptable.
2020-10-21 | 105 |  | Lan.Nguyen@team.neustar | IMA-EASE TESTING PON contain a Hyphen failed process in EASE | When submit PON with hyphen (7912724-2BAUDSC) in UOM, EASE did not return a response. Per Chuck, the hyphen is causing systemic problem. This issue need to be investigate | ORDER | Hyphen in PON not allowed | CLOSED | This is not a BRMS edit. We will discuss with the vendor when a modification can be provided.
2020-10-23 | 106 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing Reject for CSR FEAT_PP_DESCIND field | Please reopen this issue, as I am still getting reject for USOCDESCIND instead of FEAT_PP_DESCIND. TXNUM = QWCSRUSOC01 <PRESPC>18</PRESPC> <PRESPD>CSR Date should not precede 2020-10-23. USOCDESCIND must be Y. </PRESPD> | PREORDER | Testing Reject for CSR FEAT_PP_DESCIND field | CLOSED | Error message has been revised and corrected. Deplolyed successfully.
2020-10-23 | 107 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing reject for DLECCCNA | Please reopen this issue, as I have submitted Loop order (REQTYP AB), PON = QWDLEC01, and still getting below reject ERRORCODE: LSRDLECCCNA003 ERRORMESSAGE: LSR Form:Admin Section:DLECCCNA required | ORDER | Testing reject for DLECCCNA | CLOSED | Corrected error message.
2020-10-23 | 108 |  | Lan.Nguyen@team.neustar | IMA-EASE Receive invalid reject for RSTTYP when submit Resale Order | Submit Resale REQTYP EB, ACT = B and receive reject “LSRRSTTYP 003 - LSR Form:Admin Section:RSTTYP required when ACT is B” From IMA to EASE Document, CenturyLink discontinue use of RSTTYP field as RS form LNA field data will be used. We should not receive reject for RSSTYP. PON example: EBTESTACTBLNAL | ORDER | Invalid reject for RSTTYP when submit Resale Order | CLOSED | This was a negative test case and did not require work. Correcting the error message veribage is being addressed on issue 109.
2020-10-26 | 109 |  | Lan.Nguyen@team.neustar | IMA-EASE Receive invalid reject for RSTTYP when submit Resale Order | I am doing a restore service, but this is a negative test case. I purposely entered incorrect LNA, and CL should reject the LNA field and not the RSTTYP field as you are no longer support this field in EASE UOM. | ORDER | Invalid reject for RSTTYP when submit Resale Order | CLOSED | CenturyLink has updated the error message to identify the ACT-LNA combination instead of RSTTYP.
2020-10-26 | 110 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Differences | Hi – I was going through the IMA to EASE differences. Is there any way to settle on one requirement for “dashes” in in the TN fields? Thank you Address Validation by WTN Raw Loop Data By TN Looks like Listed TN is without dashes | PREORDER | IMA to EASE Differences | CLOSED | This has been altered to either take dashes or not. You can enter it both ways and get a successful response.
2020-10-28 | 111 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - Additional Test Credentials and Controlled Production Question | Have all our CCNAs, RSIDs and OCNs been added to our existing EASE LSR production credentials? | SYSTEM | Controlled Production Question | CLOSED | Provided to IT to update per request.
2020-10-28 | 112 |  | Lan.Nguyen@team.neustar | IMA-EASE PON cannot contain a dash | Today IMA allows a dash (-) in the PON value. From the latest IMA to EASE document published on 10/23 a dash is not allowed in the PON. This will cause a big issue for our in-flight orders. We need EASE to support hyphen for the orders submitting via UOM. | ORDER | IMA-EASE PON cannot cantain a dash | CLOSED | Allowing a hyphen/dash in the PON has been implemented.
2020-10-29 | 113 |  | Sarita.Singhal@team.neustar | IMA to EASE - ACT Value Z | I submit Resale (EB) request PON = LT6024316843B for following values : REQTYP: EB ACT: Z TOS: 1B While as per IMA to EASE doc, ACT Z changed to ACT V, and we were expecting reject for ACT Z, but did not received any reject for ACT value. Even I receive below reject which has ‘Z’ as valid value for ACT ERRORCODE: DL 900 ERRORMESSAGE: DL form prohibited when ACT is W, D, B, L, Y or Z | ORDER | IMA to EASE - ACT Value Z | CLOSED | Customer edit will be added to prevent UOM entry. VFO entry is already prohibited.
2020-10-29 | 114 |  | kris.schuett@arvig.com> | EASE TEST ORDER | I have one sitting out there: PON: DBLADE266. I am getting an error: Requested RuleApp is unavailable. Contact administrator. Please advise | ORDER | Error message | CLOSED | CenturyLink fixed the rule that was throwing this error.
2020-10-30 | 115 |  | Sarita.Singhal@team.neustar | IMA to EASE : "APPOINT_SCHED_RESP" node expected | I have submit Appointment Scheduling request TXNUM: TESTAPT01 TXTYP: D And received following response : "<?xml version="1.0" encoding="UTF-8"?><LSR_PO_RESP> <HDR> <MESSAGE_ID>NSTR1448</MESSAGE_ID><TPID>NSTR</TPID><MSG_TIMESTAMP>2020-10-30T02:59:17-06:00</MSG_TIMESTAMP><TXNUM>TESTAPT01</TXNUM><TXTYP>D</TXTYP><CC>5606</CC></HDR><RESP_STATUS_GRP><RESPC>18</RESPC><RESPD>Invalid Input or No Data Found</RESPD><PRESPC>18</PRESPC><PRESPD>TOS value must be populated any of (1, 2, 3, 4). PON must be populated. </PRESPD></RESP_STATUS_GRP></LSR_PO_RESP>" While we were expecting “APPOINT_SCHED_RESP” node before “RESP_STATUS_GRP”. Can you please take a look into this. | PREORDER | "APPOINT_SCHED_RESP" node expected | CLOSED
2020-10-30 | 116 |  | Sarita.Singhal@team.neustar | IMA to EASE : "FACILITY_ASSIGN_VERIFY_RESP" node expected | I have submit Feature Service Availability Request TXNUM: FSAQWEST03 TXTYP: C TOS: 1 And received following response : "<?xml version="1.0" encoding="UTF-8"?><LSR_PO_RESP> <HDR> <MESSAGE_ID>NSTR1453</MESSAGE_ID><TPID>NSTR</TPID><MSG_TIMESTAMP>2020-10-30T06:34:17-06:00</MSG_TIMESTAMP><TXNUM>FSAQWEST02</TXNUM><TXTYP>C</TXTYP></HDR><RESP_STATUS_GRP><RESPC>18</RESPC><RESPD>Invalid Input or No Data Found</RESPD><PRESPC>18</PRESPC><PRESPD>TOS must be populated, and either of B or R.</PRESPD></RESP_STATUS_GRP></LSR_PO_RESP>" 1.We expect “FEATURE_SVC_AVAIL_RESP” node before “RESP_STATUS_GRP”. Please fix it. 2.We send TOS as 1, same we send earlier in IMA format as well, now if there is any change in valid value for TOS? | PREORDER | "FACILITY_ASSIGN_VERIFY_RESP" node expected | CLOSED | The issue has been resolved. You may use numeric TOS like 1 or 2 like IMA XML. Or you may use B/R.
2020-11-03 | 117 |  | Lan.Nguyen@team.neustar | IMA to EASE TEST Number Port with Multi-Line Listing failed | Submitted LSR order REQTYP CB with two listings and receive invalid reject for OCCNA and OCC. This issue was reported and resolved earlier in the Issue Log #97. Today we have the same issue again PON LT00043899348 | ORDER | Invalid Reject | CLOSED | CenturyLink IT altered mapping to resolve this issue.
2020-11-05 | 118 |  | Sarita.Singhal@team.neustar | <RESP_STATUS_GRP> not as per Schema | 3 issues included as all are related. Issues # 1 : I am submitting FEATURE_SVC_AVAIL_REQ request. <TXNUM>TESTFSA0033</TXNUM> <TXTYP>C</TXTYP> <TXACT>A</TXACT> <TOS>1</TOS> And received good response as well. But UOM structure does not follow 2Q19 schema for RESP_STATUS_GRP fields. Issue # 2 : Same issue is with Error Response I submitted another FEATURE_SVC_AVAIL_REQ request. <TXNUM>TESTFSA0044</TXNUM> <TXTYP>C</TXTYP> <TXACT>A</TXACT> <TOS>1</TOS> And received error response as expected, as I am doing negative testing here. Issue # 3 : Same issue with APPOINT_SCHED_REQ request. <TXNUM>LTAPT503325</TXNUM> <TXTYP>D</TXTYP> <TXACT>E</TXACT> And received error response as expected, as I am doing negative testing here. | PREORDER | <RESP_STATUS_GRP> not as per Schema | CLOSED | CenturyLink fixed the issue in the schema.
2020-11-06 | 119 |  | Lan.Nguyen@team.neustar | IMA to EASE Test Pre-order TN Inquiry submit via UOM failed | Issue 1a: Submit TN Inquiry (TXTYP = B, TXACT =A ) via UOM and receive a good response with 2 TN returned. Submit TN Selection (TXTYP = B, TXACT = E) via UOM and populated TOS, SITEID, SELNUM with the TN returned in the response and received reject “Qualified address is required” In IMA today, when we submit the TN Selection, we do not have to populate the Address again from the TN Inquiry. IMA only requires the STIEID, SELNUM. Please advise why EASE require to populate the address again in the TN Selection? TXNUM = LNAVTNINQUIRY3 Issue1b: a.The reject UOM XML for TN Selection has “ <TN_RESP>” which does not follow UOM XML 2Q19. I attached the UOM XML for both TN Inquiry and TN selection for your reference. This issue is blocking our testing, could you please review ASAP? | PREORDER | Pre-order TN Inquiry submit via UOM failed | CLOSED | CenturyLink corrected this issue.
2020-11-10 | 120 |  | Sarita.Singhal@team.neustar | <RESP_STATUS_GRP> not as per Schema for TEL_N0_ASSIGN_RESP | I am submitting TEL_N0_ASSIGN_REQ <TXNUM>TESTTN002</TXNUM> <TXTYP>B</TXTYP> <TXACT>A</TXACT> And received error response which is not as per 2Q19 schema. "<?xml version="1.0" encoding="UTF-8"?><LSR_PO_RESP> <HDR> <MESSAGE_ID>NSTR1556</MESSAGE_ID><TPID/><MSG_TIMESTAMP>2020-11-10T12:22:00-07:00</MSG_TIMESTAMP><TXNUM>TESTTN002</TXNUM><TXTYP>B</TXTYP></HDR><TEL_N0_ASSIGN_RESP><CAI/><LST/><TN_RESP><RESP_STATUS_GRP><RESPC>18</RESPC><RESPD>Invalid Input or No Data Found</RESPD><PRESPC>18</PRESPC><PRESPD>Qualified address is required</PRESPD></RESP_STATUS_GRP></TN_RESP></TEL_N0_ASSIGN_RESP></LSR_PO_RESP>" While as per 2Q19 schema we are expecting this <RESP_STATUS_GRP> directly under <TEL_N0_ASSIGN_RESP> node, and there is no such <TN_RESP> node in schema. | PREORDER | <RESP_STATUS_GRP> not as per Schema for TEL_N0_ASSIGN_RESP | CLOSED | CenturyLink corrected this issue in the schema.
2020-11-10 | 121 |  | Tammy.kottschade@tdsmetro.com | EASE LSR Testing Address Validation - MN | I am attempting to perform testing for TDS with an Address Validation/Location Inquiry. The address validates in the IMA but does not validate in EASE test. Address in question: 11021 Upton Ave S, Blmgtn, MN, 55431 I have found that the only Trading Partner listed is EMBARQ, Receiver Code EMBQ with a Guideline Version of UOM19. Is separate access needed for Legacy Qwest/GUI testing for ND, MN? | PREORDER | EASE LSR Testing Address Validation - MN | CLOSED | User is able to validate address.
2020-11-11 | 122 |  | Lan.Nguyen@team.neustar | IMA to EASE - Incorrect Message Error received for MANUAL IND field | Submitted a Number Port PON = LTCBNEGTEST1 and populate NPDI = A, receive a reject “LSR Form:Admin Section:When NPDI is V, LSR Manual Ind must be Y. MANUAL IND field is not supportted in EASE, the reject message should update as “When NPDI is V, NRI must be “Y”. | ORDER | Incorrect Message Error received for MANUAL IND field | CLOSED | Error message has been updated - will be pushed to production week of 11/28
2020-11-12 | 123 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA-EASE Testing Issue- LNP-Unable to validate or submit | Could you assist us in determining what the error is on this order? Thanks ERROR : Internal Processing error ¦Code CTLS1001 Date: 11/12 PON: LA5205378LNP1 OCN/CC: 7171 CCNA: E03 DD: 11/17 AN: 5416891278673 Saved CSI: 5205378 Saved Address Validation: 5205378ADD | ORDER | LNP-Unable to validate or submit | CLOSED | NPDI=V is no longer needed in EASE if the CCNA is not a wireless provider.
2020-11-12 | 124 |  | Lan.Nguyen@team.neustar | IMA-EASE TESTING Listing Telephone Response not return service address | Today when submitting a Listing Telephone Inquiry in IMA, we receive a Service Address and CUSTID beside the Listing Address in the response. When testing in EASE, we do not receive the Service Address and CUSTID. I attached the XML examples from IMA Production versus Test in EASE. | PREORDER | Listing Telephone Response not return service address | CLOSED | DLI mapping response issue has been resolved.
2020-11-13 | 125 |  | rbyland@popp.com | Submitting a test order in EASE | Has it been suggested that the ErrorCode box be moveable outside of the Order window? Right now having the ErrorCode box being stuck inside the Order window makes it difficult to correct your errors as you keep having to move the box around to be able to see all of the fields in the form. | ORDER | Error code box | CLOSED | We will make a recommendation to the vendor for a future enhancement.
2020-11-13 | 126 |  | rbyland@popp.com | Submitting a test order in EASE | On page 74 of user guide: Step 5 under Appointment Reservation instructions says: Please Note: Saved Appointments will be retained for a period of XXXXX days. What is the XXX days? | PREORDER | Appointment Scheduler | CLOSED | EASE LSR VFO USER GUIDE has been updated. Appointments are held for 24 hours and then systematically released. Also, TN Reservation is held for 48 hours.
2020-11-16 | 127 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Controlled Product - Processing Times | Allstream is beginning to submit controlled production orders and I’m starting to receive complaints about how slow EASE LSRs is responding (see below). This has been an on-going issue we have with VFO regardless of the vendor using VFO. When compared to the response/processing time in IMA this really stands out. What can Lumen do to speed up EASE LSR production? Feedback: Also the validation and submitting process takes a really long time, probably a minute to 2 minutes each. | ORDER | IMA to EASE Controlled Product - Processing Times | CLOSED | Processing times have stablizated.
2020-11-16 | 128 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Controlled Production - Issues with Order | We are having issues with a controlled production order. Could you lend assistance? So gave my 1st order a try and I am getting the following error when validating. It is currently sitting in a Pending Validation status. Also the validation and submitting process takes a really long time, probably a minute to 2 minutes each. PON: MN5167650DS0D CCNA/CC: OGT/7482 I advised the tester (cc:d on this email) to change the CCNA to the RSID and that didn’t work I am still getting the same error after changing the CCNA to O03. I also duplicated the order incase my original CCNA of OGT caused an unfixable error upfront. The new PON is MN5167650DS0D2 and it is also getting the same error with the CCNA of O03. Also still very slow. | ORDER | IMA to EASE Controlled Production - Issues with Order | CLOSED | IT corrected the OCN/RSID issue.
2020-11-18 | 129 |  | rbyland@popp.com | Mismatch of info - LNUM field | In EASE on my PON “CONVTEST1” when I validated it said I needed to fill in the “LNUM” field on the LS form. When I hover over the description of the LNUM field it says “This field contains 5 numeric characters” but when I filled it out as 00001 it errored back and said that this field can only be 4 characters. I updated it to 0001 and the error cleared. You might want to check on and get the description of the LNUM field changed to 4 if that’s the character limit. | ORDER | LNUM field | CLOSED | We will make a recommendation to the vendor for a future enhancement.
2020-11-19 | 130 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - Address Validation - EASE Controlled Testing | Allstream is running into issues attempting to validate address is in EASE Controlled Production. Address 17910 TALBOT RD S, -STE 103, RENTON WA 98055-STE 103 The EASE address Val does not show Ste 103 but the IMA Address Val does. I tried to scroll down further on the EASE Address Val but nothing happened. I’ve attached both address validations I attempted the EASE Adval TXNUM KIMTESTADVAL and received the same response. I attempted to change Ste 103 to Unit 103 to see if that made a difference. I received an error “ We are facing GEO-ES Downstream issue, Please try again later.” (attached screen shot) | PREORDER | Address Validation - EASE Controlled Testing | CLOSED | Address issue has been resolved.
2020-12-02 | 131 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | Email Response? FW: CENTURYLINK ORDER RESPONSE: PON: TESTLNPCC, Version: 02 | I’m assuming the attached is an example of the email notifications sent by EASE. Could you confirm? If yes, this is markedly different that the emails we receive from IMA and it will Allstream to recode its internal automation. Is there anyway to just have IMA send the responses it currently sends? I am checking with my internal teams to see when our internal automation can be recoded. Please note, it might be quite some time since Allstream has its internal IT resources assigned to internal system projects. This was the scenario I was afraid of this summer when I started emailing Lumen about the need for us to review the EASE email responses early in the testing. | ORDER | Email responses | CLOSED | XML is the current supported format.
2020-12-03 | 132 |  | nancy.taylor@Allstream.com | IMA to EASE odd selections in TXACT A is AT and V is VS | Nancy attached a screen shot from PreOrder option E - Customer Service Information regarding the drop down options under TXACT | PREORDER |  | CLOSED | CenturyLink is not able to reproduce the error at this time.
2020-12-09 | 133 |  | jeanne.kulesa@synchronoss.com | Question on PON quantity | Question today – in the Q region, orders contain over 200 TNs. However, EASE typically had a limit of 200 TNs per order. Does the 200 TN limit still exist and apply the Q orders, or will be just passing thru the qty over 200 (after validation)? | ORDER | PON Quantity | CLOSED | LQ orders may contain over 200 TNs.
2020-12-09 | 134 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | Controlled Production - Auto-Populating Add Val TXNUM into LSR Didn't Work | I received the below report on a controlled production LSRPON: LA5217034LNP OCN: 7171 RDD: 12/21 TN: 360-574-2002 Issue: Unable to auto-populated validate address in LSR Address validated and saved (TXNUM 5217034ADDR) On End User Form used Prepopulate option. Address did not populate to order. Tried twice with same result. Entered address manually and used Validate. Message popped up asking if I wanted to leave order | PREORDER | Auto-Populating Didn't Work | CLOSED | This is in Production, not the test environment. We are able to use the pre-pop option.
2020-12-10 | 135 |  | Tammy.kottschade@tdsmetro.com | EEL Disconnect Error - IMA to EASE testing | I am testing an EEL disconnection order in the EASE LSR test environment. When I attempt to validate the order, ode CTLS1001 Internal Processing Error appears. The PON in in question is EELDisconnect under the Customer Code of U07. | ORDER | EEL Disconnect Error | CLOSED | LOC NUM and NAME need to be populated on the End User form. LOC NUM is only 4 digits.
2020-12-17 | 136 |  | Sarita.Singhal@team.neustar | IMA to EASE - Testing reject for EU AHN Field | I submitted order LTERS0062A (Reqtyp MB), and received below error for AHN field, while AHN not supported. ERRORCODE: EU SASN 900 ERRORMESSAGE: EU Form:Location Access Section 1:@ or Comma must be first character in SASN when populated and AHN is populated | ORDER | Testing reject for EU AHN Field | CLOSED | Error message has been corrected.
2020-12-29 | 137 |  | Sarita.Singhal@team.neustar | SERVICE Address fields return for Loop Quals Error Response | Today IMA does not return the Address fields in Loopqual Error Response, but we receive the address via EASE. Please remove the Address fields for LQ Error. TXNUM = LQERROR01 <?xml version="1.0" encoding="UTF-8"?><LSR_PO_RESP> <HDR> <MESSAGE_ID>NSTR1833</MESSAGE_ID><TPID>NSTR</TPID><MSG_TIMESTAMP>2020-12-29T11:41:14-07:00</MSG_TIMESTAMP><TXNUM>LQERROR01</TXNUM><TXTYP>H</TXTYP><CC>8424</CC></HDR><LOOP_QUAL_RESP><SVC_ADDR_GRP><SANO>86</SANO><SASD/><SASN/><SATH/><SASS/><CITY>FLAGSTAFF</CITY> <STATE>AZ</STATE><ZIP>86001</ZIP></SVC_ADDR_GRP><RESP_STATUS_GRP><RESPC>6</RESPC><RESPD>Fields Missing Address Not Found</RESPD><PRESPC>6</PRESPC><PRESPD>SANO/SASN/CITY/STATE/ZIP are missing in the Address Validation Inquiry</PRESPD></RESP_STATUS_GRP></LOOP_QUAL_RESP></LSR_PO_RESP> ERRORCODE: EU SASN 900 ERRORMESSAGE: EU Form:Location Access Section 1:@ or Comma must be first character in SASN when populated and AHN is populated | PREORDER | SERVICE Address fields return for Loop Quals Error Response | CLOSED | This is working as designed and there will be no requested modifications to this prior to conversion
2020-12-30 | 138 |  | Sarita.Singhal@team.neustar | Getting reject for ACT Y | We submitted EB order (PON EBACTY) for ACT = S, but I received reject for ACT Y ERRORMESSAGE: LSR Form:Admin Section:AN required when ACT is Y Which should be changes to ACT S. | ORDER | Reject for ACT Y | CLOSED | Error message has been corrected.
2020-12-30 | 139 |  | Sarita.Singhal@team.neustar | Response for DLI by NSTN | I have submitted DLI order (LTDLIBYNSTN) by NSTN (Non STandard Telephone Number), and receive good response. But it has multiple DLI_SVC_DET, DLI_DET, RESP_STATUS_GRP and TOS field. While as per schema TOS multiple occurrences are not allowed. Even for DLI_SVC_DET/ DLI_DET structure not looking correct. | ORDER | Response for DLI by NSTN | CLOSED | The schema has been corrected.
2021-01-12 | 140 |  | Tammy.kottschade@tdsmetro.com | Activity S & B not listed for selection | I am attempting to test the Deny & Restore functionality for Service – KB. Neither Activity of S – Suspend or B – Restore is listed for selection in the dropdown. I have verified the OCN selected is correct. See included screenshot. | ORDER | Activity S & B not listed for selection | CLOSED | Product type KB for ELL or ISDN Facility don't support deny/restore in IMA or EASE.
2021-01-14 | 141 |  | Sarita.Singhal@team.neustar | SERVICE Address fields return for Loop Quals Error Response | Sending again. Seems not fixed yet | PREORDER | SERVICE Address fields return for Loop Quals Error Response | CLOSED | This is working as designed and there will be no requested modifications to this prior to conversion
2021-01-14 | 142 |  | Sarita.Singhal@team.neustar | Getting reject for ACT Y | Sending again. Not fixed yet. | ORDER | Reject for ACT Y | CLOSED | Error message has been corrected.
2021-01-15 | 143 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Transition LNP LSR ISSUE: PON LA5224299LNP- Controlled Environment | Allstream is receiving an CTLV0060 Invalid ESP / CCNA combination on PON LA5224299LNP. In December PON LA5217034LNP completed with the same ESP, CCNA, OCN, NNSP combination. Please troubleshoot and let us know what the issue is | ORDER | Invalid ESP / CCNA combination | CLOSED | Configuration issue has been resolved.
2021-01-19 | 144 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Transition: Loss Notification Email Function - Additional Information Needed | It is my understanding that as IMA is transitioned to EASE on 1/25/2021, CLECs will not longer have the ability to look up individual Line Loss information by WTN, ECCKT, ORDW, PONW, CVD… and that Lumen will email Line Loss Notification to Allstream. Could you tell me who, how and when legacy Qwest question Line Loss Notifications will be emailed to Allstream? 1.Allstream would like loss notifications sent to a general email address. I have copied the Allstream Port Out team distribution on this email so they can advise Lumen on which email address to use. 2.We are assuming Lumen will email all line loss notifications on one email versus individual emails for each WTN, please confirm. 3.Allstream is assuming Lumen will email line loss notifications on a daily basis, the day after the line loss order completed in the Lumen systems. Please confirm our understanding. 4.I wasn’t able to find any documentation on “email” replacing the IMA Line Loss function. Please update the IMA EASE Differences document to reflect the new process. | EMAIL NOTIFICATION | Loss Notification Email Function | CLOSED | A line loss specific email will be provided. Lumen is working on a post conversion solution that will provide a searchable repository.
2021-01-19 | 145 |  | vkoski@infostructure.biz | CenturyLink Line Report | So this order I did in ease came across our line loss report, but when I got into EASE this is what I see, Not really sure what to think. I never got a rejection notice, which is what IMA would usually do. I never received any notice and the order is processed. When you run a CSR, it shows it in a state of Disconnect, | EMAIL NOTIFICATION | Line Report | CLOSED | Fix went in. Customer should be seeing notifications.
2021-01-19 | 146 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | Additional Example : IMA to EASE Transition LNP LSR ISSUE: PON LA5224299LNP- Controlled Environment | We have another example - MN5167650DS0D2 - Request to disconnect 2 loops. Receiving error hdr Pon CTLV0060 Invalid ESP / CCNA combination Like the LNP example - The PON in live EASE for LSR is populated exactly the same as a PON that “Completed” in the Test EASE for LSR | ORDER | LNP LSR Issue | CLOSED | Configuration issue has been resolved.
2021-01-20 | 147 |  | Tammy.kottschade@tdsmetro.com | Internal Processing Error - PON 4260128 - UNEP Suspend | I am receiving an Internal Processing Error when attempting to test a UNEP suspend order. PON 4260128. REQTYPE: EB ACT: S-Suspend Without details regarding the error provided, I am unable to correct what may be issues on my end. Additionally, in the IMA, we are able to submit these types of requests using only the Local Service Request Form and the End User Form. Is the change to EASE requiring now that the RS form be included? | ORDER | Internal Processing Error - PON 4260128 - UNEP Suspend | CLOSED | Order has been corrected by customer.
2021-01-26 | 148 |  | Tammy.kottschade@tdsmetro.com | Duplicate TX Type in PreOrder | This may be a housekeeping type of request. But, we’re seeing duplicate TX Type options in the PreOrder Initiation screen. Are there any plans to remove the duplicates? | PREORDER | Duplicate TX Type | CLOSED | Fixed with vendor release.
2021-01-26 | 149 |  | Lan.Nguyen@team.neustar | IMA to EASE post conversion issue | We received this error “Pre Order Response root node not configured; Please contact support.” for some CSR and Listing Inquiry transactions. Can you help to check the root cause? I validate the UOM, and they look good to me. | PREORDER | IMA to EASE post conversion issue | CLOSED | This fixed has been deployed.
2021-01-26 | 150 |  | Lan.Nguyen@team.neustar | IMA to EASE PRODUCTION Order failed for ACT Z- urgent | 00182711849IN001 – We’ve previously had FOC on this order with ACT Z before the conversion. The provisioning team can’t get it to go through now when they changed to ACT V, ELT A. Here what they tried and keep getting reject. Can you help to look at this ASAP as we cannot let the customer out of services. •ACT is V, ELT is A, MI is A. Rejected for MI of A is invalid. •Since QWEST mostly submits ELT B, I resubmitted with ELT B since MI is A. That rejected for ACT not matching original and MI of A is invalid. •removed MI altogether. Rejected for ACT does not match original and MI field indicates Full Conversion, but only a portion of the lines on the account have been entered they even try to send a SUP1 to cancel the order so they can retry with a new order but the SUP1 also got rejected. <ERRORCODE value="WO ACT 999"/> <ERRORMESSAGE value="ACT does not match original"/> <ERRORCODE value="WO 999"/> <ERRORMESSAGE value="LSR Form: MI field indicates Full Conversion, but only a portion of the lines on the account have been entered"/> | ORDER | Order failed for ACT Z | CLOSED | This has been fixed. Activity has been refreshed and order processed.
2021-01-26 | 151 |  | Lan.Nguyen@team.neustar | IMA TO EASE POST production failed for CCNA configuration | We received this error ” LSR Form:Admin Section:Invalid CCNA for product requested.” for these 2 Number Port Orders. They are valid CCNA and worked fine before the conversion. Can you please update on your end ASAP so we can resubmit these order? P1295623 2/1/2021 P5159647253 1/28/2021 | ORDER | Production failed for CCNA configuration | CLOSED | FBDL in the OCCNA is required. Customer advised of how to fix.
2021-01-26 | 152 |  | Tammy.kottschade@tdsmetro.com | System Unavailable Error | I am getting the an error indicating System Unavailable when trying to validate or send PON 12116825C | ORDER | System Unavailable Error | CLOSED | Wait 30 minutes and try again. If still persits, please open a ticket with EASE Help Desk.
2021-01-27 | 153 |  | dawn.denny@tdsmetro.com | EASE - GEO-ES Downstream issue Error | We are receiving this error when attempting to validate any addresses; We are facing GEO-ES Downstream issue, Please try again later. | PREORDER | GEO-ES Downstream issue error | CLOSED | Zip had an * in it. User corrected
2021-01-27 | 154 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | EASE LSR - Internal Server Error - Multiple User Impact | Some Allstream users are getting an Internal Server Error when trying to log into to EASE LSR. It was working fine earlier today but is not responding at the moment - | SYSTEM | EASE LSR - Internal Server Error - Multiple User Impact | CLOSED | Server issue has been resolved.
2021-01-26 | 155 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - EEL EU Page Errors | MR5226487EELD1 Regardless of where we put the location information on this EEL disconnect (EU form or the RPL form) we are getting an error “EU Form Required” (even if the EU form is populated). Could you send me an EEL disconnect example so I can confirm whether we have some other error that is kicking off the EU Form Required error | ORDER | EEL EU Page Errors | CLOSED | EEL disconnect example provided
2021-01-26 | 157 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - EEL EU Page Errors | I finally got MR5226487EELD1 EEL Disconnect to Confirmed status but I had to add the ECCKT - 3 different times on the RPL form. Could you get me an example of how to submit EEL disconnects and confirm that the ECCKT needs to be on the RPL 3 different times? Also, we continued to receive errors indicating the issue was on the EU form but that was not correct. The “EU Form” errors cleared when I added the ECCKT to the RPL form 3 times. It is really important that we get accurate error messages. This order took way more guessing then I am comfortable with. Thanks. | ORDER | IMA to EASE - EEL EU Page Errors | CLOSED | EEL disconnect example provided
2021-01-25 | 158 |  | akhil.yarragangu@comcast.com | Tn not on end-user's account | I am seeing some responses on SUPP as “<TN> not on end-users account” when submitting through EASE but on the Same request on initial PON is confirmed which was sent out using IMA. Please see the below details. PON : “202059981” initial version 00 is confirmed on Due date ‘20210126’ but same PON with Date change with version ‘01’ has been rejected with ‘503-363-8066 not on end-user's account’. | ORDER | Tn not on end-user's account | CLOSED | Fix was implemented 02-04-21.
2021-01-27 | 159 |  | Tammy.kottschade@tdsmetro.com | REQTYP - Conflicting information for UNE-P | I am attempting to submit a request for UNE-P lines. USOC: U5R & U5RAX. I had submitted with the REQTYP of EB. PON 12116825C and it was rejected stating invalid request type. I am now trying to submit a new request for the same numbers with the REQTYP of MB and the PON is erroring stating Invalid REQTYP/TOS combination. PON 12116825C2. The TOS is 1AM – Business, Multi-Line Measured | ORDER | REQTYP - Conflicting information for UNE-P | CLOSED | Rmoved dash after the REQTYP and it was successful
2021-01-27 | 160 |  | dawn.denny@tdsmetro.com | Processing LSR - Address validation error | This was also brought up in the IMA to EASE status call. We are receiving the below error and the address had been validated with trying both U07 and 7036 as the OCN? | ORDER | Address validation error | CLOSED | Order has been fixed. FOC has been issued.
2021-01-28 | 161 |  | dawn.denny@tdsmetro.com | Invalid REQ Type/COS combination - EEL LSR - PON 12077545 | Can you please take a look? Per the IMA to EASE differences REQTYP should be KB rather than MB. I am attempting to submit a request for EEL LSR I had submitted with the REQTYP of KB PON 12077545 and it was rejected stating invalid request type/COS Combination – Remarks: Account Type is EEL. | ORDER | Invalid REQ Type/COS Combination | CLOSED | The LSR SPEC field must have LOOPEEL for the EEL product
2021-01-28 | 162 |  | nwilson@truleap.net | ADMIN View | Researching ADMIN views and visability | SYSTEM | ADMIN View | PENDING | Pending vendor fix coming in the 17.16 release end of March. Will be April when this is deployed at LUMEN will need to test in our environment.
2021-01-29 | 163 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - Directory Listing Suite Address | Can you provide me with instructions on how to get a Suite included in a Directory Listing. See below for details. Thank you. | ORDER | Directory Listing | CLOSED | This is a backend system issue and has been referred for resolution. This issue does not reflect the IMA to EASE conversion.
2021-02-01 | 164 |  | Lan.Nguyen@team.neustar | IMA to EASE post conversion issue - PreOrder Response Root node not configured | We run into this problem again. Below is the list of transactions. csr SPT003489367 Pre Order Response root node not configured, Please contact support. | PREORDER | Root Node | CLOSED | Issue was resolved with 2-12-21 Maintenance Release
2021-02-01 | 165 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Issue or ??? FW: FOC Summary PON: LA-5216714-POTS VER: EC VER: 03 | One of Allstream's provisioners got the below FOC for a loop order we accepted on 12.15.2020. Could you tell me why Lumen sent the 2nd FOC? Is this related to the IMA to EASE transition or something else. Thank you | ORDER | 2nd FOC | CLOSED | 2nd FOC was manually issued. This issue does not reflect the IMA to EASE conversion.
2021-02-02 | 166 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | Not added to A07 - : Need additional CCNAs, OCNs added for Directory Listing | Hi Letty – we are still not seeing CCNA IOC or CC 5061 under Managed ESP A07 or 7174. Could you ask where the added the OCN? Thanks | ORDER | Not added to A07 | CLOSED | CC 5061 has been added under A07
2021-02-02 | 167 |  | Lan.Nguyen@team.neustar | IMA to EASE - Pre-Order Error "Response Root Node not configured" | Received reject “Preorder Response Root Node not configured: Please contact support” when submitting CSR, AV, and Listing Telephone Inquiry The same issue #149 was fixed last week, but we receive the error again in the last few days. Example: NDLI21634369 3603855225 AVQWS00002849160 NCSR21632035 SPT003503423 NCSR21632879 | PREORDER | Root Node | CLOSED | Issue was resolved with 2-12-21 Maintenance Release
2021-02-02 | 168 |  | Tammy.kottschade@tdsmetro.com | System Unavailable Error | When attempting to validate EASE LSR 11369285 I am getting the following error. I called the Wholesale Systems help desk (as listed in the Whom to Call and When section of the EASE LSR User Guide) and spoke with a person who said because I’m in the Lumen QC region she has no information on what to do to assist. She contacted the Lumen QC region folks who told me she doesn’t have any information on this type of error. She is able to assist when there are defined errors, but not something like this. And that there is no EASE Systems help desk. | ORDER | System Unavailable Error | CLOSED | The name is too long. Max length is 25 characters <NAME>Innovated Metal Fabrication</NAME> is 27 characters
2021-02-03 | 169 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE Issue: EASE Autopopulating Listing Issue | I’m not certain if this is a EASE issue or a training issue but I received the following report The EASE Repopulate(Recap in IMA) function on the DL tab so far has worked only for LML listings. I attempted to Repopulate 5 listings(LML and 4 LAL’s) and it only repopulated one of the LAL’s. Saved TXNUM for the listings is: 264 T - Listings for Telephone Number EMBARQ A07 2021-02-03 11:57:01.144 All the listings are included in the pre order TXNUM above but they do not repopulate while in the order. I tried as well PON TESTLISTAUTOPOP and was not able to get the LAL listings to pre-populate on the DL form either. Thanks for your help | PREORDER | EASE Autopopulating Listing Issue | CLOSED | This has been fixed.
2021-02-03 | 170 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | EU Errors | Could you tell me why we were getting EU errors when adjusting the RPL form got the order to go through? | ORDER | EU Errors | CLOSED | <ERROR_REJECT_INFO> <ERROR_REJECT_CODE>EU 001</ERROR_REJECT_CODE> <ERROR_REJECT_DESC>EU form required</ERROR_REJECT_DESC> </ERROR_REJECT_INFO> The RPL form didn’t have the NAME field. The EU form has the NAME field and needs to populated.
2021-02-05 | 171 |  | Lan.Nguyen@team.neustar | IMA - EASE Post conversion Order with multiple response - URGENT | Our provisioning report an issue where we received 2 responses with 2 due date in one UOM transaction for the same PON. We currently map only the first LR and pick up the first due date. This will cause an issue when activate the port. Can you please investigate this issue ASAP? Part #2: If I read correctly, since the schema is not repeating at the order level, we will have to map from the LR level (the 2nd LR) when the PIA = 2 (due date change by CL) to pull the correct due date and ignore the first LR. Is that right? I also noticed in the IMA Notice, there is a second PIA = 12 and the AN value changed but I don’t see that in the EASE XML. Can you check it please? | ORDER | Order with multiple response | CLOSED | 1 PON created 2 service orders with 2 different due dates REF ORDER DD STATUS 1 D21668929 02/23/2021 Issued 2 D21668930 02/25/2021 Issued I believe this is due to the schema not repeating at the order level. Attached is what it would look like in the old IMA way. AN's have been mapped to the EAN fields.
2021-02-05 | 172 |  | CLEC Call | Wild Card for ZIP | Is there a wild card that you can use if you don't know the zip like *? | PREORDER | Address validation | CLOSED | This is not supported in IMA today and will not be looked at in EASE.
2021-02-05 | 173 |  | CLEC Call | Edit for out of IMA hours | Track when edit is placed for out of IMA hours | ORDER | Edit needed | CLOSED | Adding an hour on the end of the day. Back end systems have availability to support.
2021-02-01 | 174 |  | Lan.Nguyen@team.neustar | IMA TO EASE Production preorder failed - Neustar | Can you please help to look at these 2 issues? 1. We had a few preorder transactions submitted to Qwest and could not find the responses. If Qwest sent the response, can you please provide me the UOM XML? NCSR21576495 NDLI21569999 NDLI21561293 2. We received response for TXNUM that not initiated from our system. I provided a few examples. | PREORDER | Associated to the Root Node issue | CLOSED | Issue was resolved with 2-12-21 Maintenance Release
2021-02-05 | 175 |  | kris.schuett@arvig.com> | EASE question | Is there a way that the FCP#/ information can be located or kept track of in EASE? We have five locations in MN where we need to utilize these and for billing purposes and record keeping it would be nice to be able to validate those just like we do for the regular unbundled loops. Are we the only company that uses Meet Point's ? | ORDER | EASE Questions | CLOSED | Its possible to use MEET POINT to look up POTSSPLITS and CABCONNs. I have only seen Meet Points starting with VCE. And VDA.
2021-02-05 | 176 |  | kris.schuett@arvig.com> | EASE question | Can you please look at PON: DISCSTAPLES2521. On this order I included two different 3LXFU's for the same LOCA-LOCZ to disconnect. I did that previously in IMA and on the completion email for this PON it shows two 3lxfu circuits being disconnected so I am assuming I can continue to do that as long as the CFA's are in the LOCA- LOCZ? | ORDER | EASE Questions | CLOSED | Yes you can disconnect multiple ECCKTs on a single LSR. Caveat - I believe the CSIE will want them to exist on the same CSR though.
2021-02-05 | 177 |  | kris.schuett@arvig.com> | EASE question | Is there a way in EASE to validate more than 100 CFA's at a time? In all of our area's we have between 1-1000 for each location and it would be great to validate all at once instead of only doing 1-100, 101-200 etc. Would save alot of Pre-Order work and TN-NUM's . | ORDER | EASE Questions | CLOSED | It’s a down stream limitation and IMA also does only chunks of 100 at a time
2021-02-05 | 178 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE CCNA/CC and LSR Bill ACNA Mismatch | Below are the 2 PONs were there was a mismatch between the LSR Admin CCNA/CC and the LSR Bill ACNA. Please confirm this will not case an issue when the order is posted to billing. Thanks MN5036343EOCD MN5141453DS0D | ORDER | LSR Bill ACNA Mismatch | CLOSED | Verified with order typists in the service center and confirmed that it will not create a problem
2021-02-08 | 179 |  | rbyland@popp.com | Saved validated address not Pre-Popping | saved validated addresses are not pre-populating correctly (address fields and city names switch around from the exact match that was validated). | ORDER | Validated Address is not Pre-Popping | CLOSED | Issue has been resolved. Did a TEST Pre-Order and started an AB order under P01 and everything is working as expected.
2021-02-08 | 180 |  | rbyland@popp.com | Inability to Issue a Disconnect for multiple circuits | The other issue is the inability to issue a disconnect for multiple circuits on the same PON. This was a functionality in IMA that based on the training information prior to EASE launch seemed something that was possible in EASE. We need this ability as we often issue PONS with multiple circuits disconnecting from the same address. IMA did not require an AN for these type of orders and did not require a separate PON per circuit. | ORDER | Disconnect multiple circuits on the same PON | CLOSED | Multi-circuit disconnects may be submitted in EASE by using the LS_SVC_DET section along with the SVC_DET_GRP section on the LS form as long as they are on the same CSR and they are at the same address.
2021-02-10 | 181 |  | Tammy.kottschade@tdsmetro.com | System Unavailable Error | When attempting to validate EASE LSR 11369285 I am getting the following error. I called the Wholesale Systems help desk (as listed in the Whom to Call and When section of the EASE LSR User Guide) and spoke with a person who said because I’m in the Lumen QC region she has no information on what to do to assist. She contacted the Lumen QC region folks who told me she doesn’t have any information on this type of error. She is able to assist when there are defined errors, but not something like this. And that there is no EASE Systems help desk. | ORDER | System Unavailable Error | CLOSED | Enduser name Innovated Metal Fabrication is 2 characters too long. IMA name length limit is 25
2021-02-15 | 182 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE: Listings for Telephone Numbers | Allstream is having difficulty pulling LTI requests this morning in the legacy Qwest territory. Could you review the below example and let us know if there is an EASE issue? Thanks The request is for TN 6512228973 and the CC is 5644. There is an active record in DLIS. This is the response we received. | PREORDER | Listing for Telephone Number Issue | CLOSED | IT resolved the issue
2021-02-16 | 183 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - Directory Listing Suite Address | I see on the issues log that this issue was closed. I must have missed the meeting where Lumen shared the resolution. How do we add suite to a listing in WA and OR. | ORDER | Directory Listing Suite Address | CLOSED | We map LALO to it. If it is provided, we map it and go on. Possible timing issue, as we believe this has been fixed. Asked Kim to subit a change order to add the suite.
2021-02-19 | 184 |  | 0 | n/a | Provide list of blocking values for order. IMA had drop down list of values - need to find a way to reference. | ORDER | BLOCKING VALUES | CLOSED | Letty will send out the information in a notice.
2021-02-19 | 185 |  | dawn.denny@tdsmetro.com |  | Facility Availability Issue | PREORDER | not referencing information for working circuits. | CLOSED | This issue was fixed with the maintenance release on March 5th.
2021-02-23 | 186 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - EASE Unavailable? DL Pre-Order and Order Issues | I’m received the following report this morning. Yesterday and today, during normal business hours, the DL pre order was not working/timing out and now today I am unable to submit an order. I am getting the following error. System Unavailable - error message | ORDER | IMA to EASE - EASE Unavailable? DL Pre-Order and Order Issues | CLOSED | RTR edit is in place.
2021-02-24 | 187 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - EASE Unavailable? DL Pre-Order and Order Issues | We’ve tried the below and a number of different various of these fields, all of them timeout OCN 5744 | PREORDER | Listings for Telephone Number | CLOSED | This issue was fixed with the maintenance release on March 5th.
2021-02-24 | 188 |  | Isaacs, Kim <Kim.Isaacs@allstream.com> | IMA to EASE - EASE Unavailable? DL Pre-Order and Order Issues | This is not the only one either - We can’t pull the following LTNs either 3607542203 3603524426 3603578011 3603524901 3603578016 | PREORDER | Issue with LTN's | CLOSED | This issue was fixed with the maintenance release on March 5th.
2021-02-26 | 189 |  | vkoski@infostructure.biz - CLEC Call | Date is not PRE-POPPING | Complete the appointment scheduler in PREORDER, but the date is not pre-popping into the PON while creating the order. | ORDER | Date is not PRE-POPPING | CLOSED | Pre-Pop immediatley. You can't key into the fields and then try to pre-pop.
2021-03-03 | 190 |  | Lan.Nguyen@team.neustar | IMA-EASE Directory Listing order failed - Urgent Issue | We received a below reject for all Directory Listing order (REQTYP JB) starting this week. Qwest never requires this field in the past for JB; Do you know what has changed? Can you please take a look ASAP as all of our customer’s DL orders rejected? <ERRORCODE value="QW067"/> <ERRORMESSAGE value="RTR MUST EQUAL C OR D."/> Below are some examples from one customer. DADL185208ACMTM1 DADL180225ACMTM1 | ORDER | Directory Listing order failed | CLOSED | BRMS edit has been modified.