## Slide 1: CMP C2E Billing Migration CLEC / RevGen Intro
Project Status
December 20, 2023

## Slide 2: Agenda
Introductions
Our Understanding
Key Phases & Proposed Timeline
Roles & Responsibilities
Key Activities & Deliverables
Questions
Next Steps

## Slide 3: Team Introductions
Neel Pelser
Sr. Telecom & OSS / BSS SME
Ann McKissick
Project Manager
Brian Young
Sr. Delivery QA Lead
Delicia Tucker
Lumen Account Lead
Eric Hall
Billing System Test Lead
Ron
Leighton
Jill Martain
IBM & CLECs

## Slide 4
Our Understanding
The Lumen Enterprise Customer Financial Services (CFS) team sought a neutral 3rd party testing facilitator to provide data, expertise, and guidance that will assist Lumen and CLECs to assess Lumen’s readiness to transition from CRIS Billing System to End State Billing System (Ensemble).
Goals
Assist the parties in identifying parameters and baseline metrics to ensure comparable functionality, flow through rates
Assist the parties in adhering to the timetable for testing and the metrics for success
Provide an “observe and report” function by having access to the OSS test results, with the authority to report the statistics to the commission and each affected CLEC
Assist in trying to resolve issues and disputes that arise, prior to either party seeking dispute resolution
Outcomes
Stakeholders held accountable to deadlines, metrics, and milestones
Documentation and acceptance of new/unique test cases as needed per CLECs’ requirements and feedback
Confirmed parameters and baseline metrics for functionality, flow through rates
Verified test results and identified test cases where deficiencies are identified (as needed)
Confirm test cases are completed and requirements are met
Go/No Go criteria documented, validated, and agreed upon for deployment among key stakeholders

## Slide 5: Key Phases
Areas of Focus
1
2
3
Test Planning |  | Preparation phase to identify key IT and business stakeholders, existing documentation, and system infrastructure to develop overall test plan and timelines, establish communication plan, and determine appropriateness of test scenario/cases
Test Execution |  | Execution phase where team will manage and hold stakeholders accountable to testing plan, timelines, and milestones while coordinating and communicating results of test cases and identified risks/issues
Deployment Readiness |  | Concluding phase for team to prepare materials and criteria to enable and align all stakeholders to make an informed decision to proceed with deployment of billing migration

## Slide 6: Proposed Execution Approach
Workstream | Dec – 23 | Jan – 24 | Feb – 24 | Mar – 24 | Apr – 24 | May – 24 | Jun – 24
Test Planning |  |  |  |  |  |  | 
Test Execution |  |  |  |  |  |  | 
Deployment Readiness |  |  |  |  |  |  | 
Stakeholder Confirmation
Based on our understanding of Lumen’s objectives, RevGen’s responsibilities will be performed over 3 phases of work based on testing timelines.
Test Documentation Review
Test and Communication Plan Development
System and User Readiness Assessment
Test Execution Status Updates
Issue Triage & Management
Test Result Verification
Deployment Criteria and Plan Development
Test Execution – 1/12/24
Project Start
Deployment - 5/20/24
Go / No-Go - 5/16/24

## Slide 7: Team Roles & Responsibilities
Project Role | Team Member | High Level Responsibilities
Sr. Delivery QA Lead | Brian Young | Provide strategic direction and guidance to RevGen team Provide overall engagement oversight and escalation point of contact Foster engagement success and client satisfaction
Sr. Telecom & OSS / BSS SME | Neel Pelser | Provide technical and industry expertise to project team and stakeholders Provide appropriate process and transactional guidance and support to project team and testing resources Review quality of test results and verification Support detailed understanding of customer, product, pricing, event, contract, and components of transaction flow
Project Manager | Ann McKissick | Manage to the approved test plan and timeline Develop and implement a communication plan Develop test results dashboard and status reports Communicate test results to key stakeholders Host key stakeholder meetings (e.g., feedback sessions, status meetings) Manage risks and issues, escalate as needed
Billing System Test Lead | Eric Hall | Develop the test plan and timeline Inventory and validate test cases Review and identify efficacy of testing Conduct ad hoc verification of test results Propose additional test requirements as needed to satisfy CLEC requirements Host standups to discuss test execution status and any issues Review deployment criteria and confirm readiness Support risk mitigation and issue resolution

## Slide 8: Stakeholder Roles & Responsibilities
Project Role | Team Member | High Level Responsibilities
Project Sponsor | Ron Leighton | Provide guidance, support, prioritization, and approvals as required for RevGen to accomplish project objectives Provide support and help liaise with Lumen and/or IBM leadership as need
Lumen Testing & Development Delivery Manager (confirm) | Jill Martain | Confirm Lumen IT and/or IBM project timelines Provide support and help liaise with Lumen IT and/or IBM leadership as need Management of requirements/testing related questions with CLECs
Test Execution | IBM | Execute test cases and scenarios Document results of testing
Test Resolution | IBM and Lumen IT | Resolve issues identified during testing
UAT Test Execution & Approval | CLECs | Review and approve unique test cases

## Slide 9: Key Activities & Deliverables
Phase | Key Activities | Deliverables
Test Planning | Identify and confirm key IT and business stakeholders at Lumen, including IBM Identify and confirm CLEC participation and key participants Inventory and review test cases provided by Lumen development & testing teams Create additional new test cases and/or modify existing test cases as needed based on internal review and per CLECs’ requirements/feedback Develop overall test plan and timeline and seek approval from CLECs and Lumen Confirm parameters and baseline metrics for functionality, flow through rates, and load testing are included in the test plan Define and socialize the communication and reporting plan Confirm issue and resolution process and timing with key stakeholders Confirm collaboration platform for the project (e.g., Jira, DevOps, etc.) and gain access Establish meeting cadence with key stakeholders Analyze customer base and transaction types to determine appropriate sample size Confirm system and user connectivity are working appropriately | Stakeholder List Communication Plan Test Plan & Timeline RAID Log New/modified Test Cases (as needed)
Test Execution | Manage and confirm adherence to the testing plan and timeline Manage and hold stakeholders accountable to deadlines, metrics, and milestones for success Monitor and record test case progress and results Conduct ad hoc verification of test results Coordinate triage and resolution of failed test cases Compile test results and status updates to share with stakeholder groups Develop additional test cases where deficiencies are identified (as needed) Review resolution of test cases Confirm test cases are completed and testing requirements are met Identify and mitigate risks as needed Host stakeholder meetings to discuss test results, status updates, and any issues | Status Updates Test Results Dashboard Test Results Verification & Confirmation Documentation
Deployment Readiness | Prepare materials and checklist for go/no-go decision Facilitate deployment readiness meetings in collaboration with key stakeholders Validate go/no-go criteria have been met Obtain go/no-go agreement among key stakeholders Finalization of deliverables and project wrap up | Final Test Results for Go/No-Do Decision Go/No-Go Approval & Confirmation Documentation

## Slide 10: Question & Answer

## Slide 11: Next Steps
  Gather requirements, dependencies, Risks from CLECs
  Review test cases identified by CLECs on …..
  Propose test readiness call with CLECs on 1/5/23
  Identify meeting cadence and communication plan for CLECs

## Slide 12: Thank You!