## Sheet1
DATE | FROM | ISSUE/QUESTION | RESOLUTION/ANSWER
2023-05-17 | Kim Isaacs - Allstream | Need CRIS BAN list | Please submit email to cmpcomm@CenturyLink.com with a list of your RSID & ZSID codes, and we will pull your CRIS BANs
2023-05-17 | Kim Isaacs - Allstream | Need centralized place for all CRIS to Ensemble documents | We have created a page on the CMP website to house these documents
2023-05-17 | Kim Isaacs - Allstream | CRIS to Ensemble Differences List | Once this is completed it will be placed on the CMP website under the CRIS to Ensemble Conversion
2023-05-17 | Martha Jenkins - Earthlink | Will this be a 1 BAN to 1 BAN? | It will be BAN to BAN relationship except where summary billing in in effect our goal is to move into one Ensemble BAN. Ensemble BAN's will be provided at a later date.
2023-05-17 | Olga Shteynberg - BCN | Will these changes also be applied to the daily usage file or monthly usage files? | Yes, we will also be migrating the usage files
2023-05-17 | Kim Isaacs - Allstream | Do the CRIS CSR's feed into EASE for preorder query on a CSI | The new CSR's will feed into EASE as they do today.
2023-05-17 | Kim Isaacs - Allstream | Need to have testing CSI retrieval as part of the testing | Yes, we will have CSI testing during the testing time frame
2023-06-20 | Rosie Knudsen - Comcast | Does this have any impact to Pre-Order or LSR Number Portability? | It does impact pre-order as instead of USOCs on the CSR you pull it will be in price plans and feature codes instead of the USOCs you see today. Ordering for LSR Number Portability, the process is the same after pre-order is completed.
2023-07-12 | Andrea Smith - Comcast | Is there going to be a list provided for USOC to map to the price plan and feature codes? | Sent notice 10/10/23
2023-07-12 | Unknown Guest | When will account mapping be put out? The new account vs the old account | Sent December 2023/January 2024
2023-07-12 | Kim Isaacs - Allstream | Need tech specs for EDI format | Sent notice 9/27/23
2023-07-12 | Kim Isaacs - Allstream | Need to know what is happening with BillMate data | Sent notice 11/7/23
2023-07-12 | Unknown Guest | Direct team for resell/wholesale customers? | No. You can send any questions to CMPCOMM@centurylink.com
2023-07-12 | Joshua Kidd - Zayo | Are bill dates going to change? | No, however there are two bill cycles that aren't supported by Ensemble (cycles 4 and 26) we will check to see if any of the accounts fall into those cycles.
2023-07-19 | Kim Isaacs - Allstream | What will happen with the USOC finder tool? | There will no longer be a need for this as Ensemble has more of a description in the price plans & features.
2023-11-14 | Anchy Trinidad | When are w going to get the mapping of the accounts? | Sent December 2023/January 2024
2023-11-14 | Anchy Trinidad | Will we have to load the accounts into Control Center ourself or will you do that | Control Center has both CRIS & Ensmble accounts loaded today, with the understanding the Ensemble accounts are live accounts that exist in Ensmble today. We are working on the test scenarios
2023-11-14 | Anchy Trinidad/Kim Isaacs | How will we get the daily usage files? | You will continue receiving your usage files in the same manner you do today, there will be no changes
2023-11-14 | Rosetta Knudsen | This isn't replacing control center is it? | No